## Task_Data
ID | Active | Task_Mode | Task_Name | Duration | Start_Date | Finish_Date | Predecessors | Resource_Names | Outline_Level
1 | Yes | Auto Scheduled | Discovery Collaboration | 225 days | 2021 January 01 00:00 | 2021 November 11 16:00 |  |  | 1
2 | Yes | Auto Scheduled | Engage Clinical on acceleration strategy for candidate | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 | 3SS |  | 2
3 | Yes | Auto Scheduled | [BTx date] Lead Development | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
4 | Yes | Auto Scheduled | Stage III Molecular Assessment | 225 days | 2021 January 01 08:00 | 2021 November 11 16:00 |  |  | 2
5 | Yes | Auto Scheduled | Make SSI constructs (2x SSI 2.0)- upto 4 constructs | 20 days | 2021 January 01 08:00 | 2021 January 28 16:00 | 3SS |  | 3
6 | Yes | Auto Scheduled | MAT Review of Full read-out of the data from Stage-II | 0 days | 2021 February 11 16:00 | 2021 February 11 16:00 | 5FS+10d |  | 3
7 | Yes | Auto Scheduled | Bioassay Transfer | 10 days | 2021 January 29 08:00 | 2021 February 11 16:00 | 6FS-10d |  | 3
8 | Yes | Auto Scheduled | Transfer bioassay critical reagents to PS | 5 days | 2021 February 12 08:00 | 2021 February 18 16:00 | 7 |  | 3
9 | Yes | Auto Scheduled | Transfer 5 vials to cell line development | 1 day | 2021 March 02 08:00 | 2021 March 02 16:00 | 6FS+4d,20 |  | 3
10 | Yes | Auto Scheduled | TS0 Scale up expression (20L) | 15 days | 2021 March 10 08:00 | 2021 March 30 16:00 | 9FS+5d |  | 3
11 | Yes | Auto Scheduled | TS0 Purification (ProA + non-LCLV TMAE and/or CHA and/or HIC (SEC Optional)) | 15 days | 2021 March 31 08:00 | 2021 April 20 16:00 | 10 |  | 3
12 | Yes | Auto Scheduled | Analysis of CHO SSI Material Available-Stage III (TS0) | 5 days | 2021 April 21 08:00 | 2021 April 27 16:00 | 11 |  | 3
13 | Yes | Auto Scheduled | CHO SSI Material Available-Stage III (TS0) | 0 days | 2021 April 27 16:00 | 2021 April 27 16:00 | 12 |  | 3
14 | Yes | Auto Scheduled | Bioassay Development | 66 days | 2021 April 28 08:00 | 2021 July 28 16:00 | 8,7,13 |  | 3
15 | Yes | Auto Scheduled | Stage III Molecular Assessment - Analytical | 14 days | 2021 April 28 08:00 | 2021 May 17 16:00 | 13 |  | 3
16 | Yes | Auto Scheduled | PhRD Molecular Assessment III | 142 days | 2021 April 28 08:00 | 2021 November 11 16:00 | 13 |  | 3
17 | Yes | Auto Scheduled | Handling and Pharmaceutics Assessment | 10 days | 2021 April 28 08:00 | 2021 May 11 16:00 | 13 |  | 3
18 | Yes | Auto Scheduled | PhRD MA III stability readout (28w) | 2 days | 2021 November 10 08:00 | 2021 November 11 16:00 | 13FS+140d |  | 3
19 | Yes | Auto Scheduled | PharmSci BioTx mAb CS-FIH | 905 days | 2021 March 02 08:00 | 2024 August 19 16:00 |  |  | 1
20 | Yes | Auto Scheduled | Prioritization/Endorsement of Resources and Funding | 0 days | 2021 March 02 08:00 | 2021 March 02 08:00 | 21SS-88d |  | 2
21 | Yes | Auto Scheduled | [BTx date] Candidate Selection (CS) | 0 days | 2021 July 01 16:00 | 2021 July 01 16:00 | 3SS+130d |  | 2
22 | Yes | Auto Scheduled | DSRD Reg Tox Safety Study (3 month in life) | 165 days | 2022 July 11 08:00 | 2023 February 24 16:00 | 141 |  | 2
23 | Yes | Auto Scheduled | Non-Clinical Overview (NCO) | 0 days | 2023 February 28 16:00 | 2023 February 28 16:00 | 141FS+167d |  | 2
24 | Yes | Auto Scheduled | Final Approved Protocol (FAP) | 0 days | 2023 March 23 16:00 | 2023 March 23 16:00 | 23FS+17d |  | 2
25 | Yes | Auto Scheduled | WWRA IND Publishing & Submission Activities | 25 days | 2023 March 24 08:00 | 2023 April 27 16:00 | 24,23 |  | 2
26 | Yes | Auto Scheduled | [BTx date] IND/IMPD Submission | 1 day | 2023 April 28 08:00 | 2023 April 28 16:00 | 25,23FS+20d |  | 2
27 | Yes | Auto Scheduled | Regulatory Review | 22 days | 2023 May 01 08:00 | 2023 May 30 16:00 | 26 |  | 2
28 | Yes | Auto Scheduled | Investigator Initiation Package (IIP) Approved | 0 days | 2023 May 17 08:00 | 2023 May 17 08:00 | 29SS-5d |  | 2
29 | Yes | Auto Scheduled | First Subject First Visit (FSFV) | 0 days | 2023 May 23 16:00 | 2023 May 23 16:00 | 26FS+17d,23FS+32d |  | 2
30 | Yes | Auto Scheduled | First Subject Dosed (FSD) | 0 days | 2023 June 06 16:00 | 2023 June 06 16:00 | 23SS+45d,27,29FS+10d |  | 2
31 | Yes | Auto Scheduled | [BTx date] Phase 1 Start | 0 days | 2023 August 04 16:00 | 2023 August 04 16:00 | 30,27,263SS |  | 2
32 | Yes | Auto Scheduled | SAD Study | 65 days | 2023 August 07 08:00 | 2023 November 03 16:00 | 31 |  | 2
33 | Yes | Auto Scheduled | MAD Study | 65 days | 2024 May 21 08:00 | 2024 August 19 16:00 | 32FS+141d |  | 2
34 | Yes | Auto Scheduled | Development & Mfg of Supplies for RegTox & FIH | 1940 days | 2021 January 01 08:00 | 2028 June 08 16:00 |  |  | 1
35 | Yes | Auto Scheduled | Team Activities - Preclinical and Team Supplies milestones | 593 days | 2021 April 27 16:00 | 2023 August 04 16:00 |  |  | 2
36 | Yes | Auto Scheduled | PS BTx Start Trigger | 0 days | 2021 April 27 16:00 | 2021 April 27 16:00 | 38SS |  | 3
37 | Yes | Auto Scheduled | PS BTx End Trigger | 0 days | 2023 August 04 16:00 | 2023 August 04 16:00 | 31 |  | 3
38 | Yes | Auto Scheduled | TS0 Available | 0 days | 2021 April 27 16:00 | 2021 April 27 16:00 | 13 |  | 3
39 | Yes | Auto Scheduled | TS1 Available | 0 days | 2021 October 12 16:00 | 2021 October 12 16:00 | 70 |  | 3
40 | Yes | Auto Scheduled | TS2 Available | 0 days | 2021 December 28 16:00 | 2021 December 28 16:00 | 81 |  | 3
41 | Yes | Auto Scheduled | pDNA Cell Banking & Manufacture | 145 days | 2021 May 26 08:00 | 2021 December 14 16:00 |  |  | 2
42 | Yes | Auto Scheduled | E. coli Host Transformation | 5 days | 2021 May 26 08:00 | 2021 June 01 16:00 | 63 |  | 3
43 | Yes | Auto Scheduled | Small Fermentation Evalution (10L - CPD) | 10 days | 2021 June 02 08:00 | 2021 June 15 16:00 | 42 |  | 3
44 | Yes | Auto Scheduled | Pre-MCB Generation & Tech Transfer to Cell Banking | 10 days | 2021 June 09 08:00 | 2021 June 22 16:00 | 43FS-5d |  | 3
45 | Yes | Auto Scheduled | MCB cell bank preparation activities | 15 days | 2021 June 02 08:00 | 2021 June 23 08:00 | 46SF |  | 3
46 | Yes | Auto Scheduled | Manufacture MCB | 20 days | 2021 June 23 08:00 | 2021 July 20 16:00 | 44 |  | 3
47 | Yes | Auto Scheduled | Cell Bank Environmental Monitoring | 35 days | 2021 June 23 08:00 | 2021 August 10 16:00 | 46SS |  | 3
48 | Yes | Auto Scheduled | Test & Release MCB | 60 days | 2021 July 21 08:00 | 2021 October 12 16:00 | 46 |  | 3
49 | Yes | Auto Scheduled | MCB Full Release characterization/ testing | 85 days | 2021 July 21 08:00 | 2021 November 16 16:00 | 46 |  | 3
50 | Yes | Auto Scheduled | MCB Final Documentation | 20 days | 2021 November 17 08:00 | 2021 December 14 16:00 | 49 |  | 3
51 | Yes | Auto Scheduled | Transgene Small Scale Evaluation & Additional Process Dev. (If Needed) | 30 days | 2021 July 28 08:00 | 2021 September 08 08:00 | 52SF |  | 3
52 | Yes | Auto Scheduled | Transgene Tech Transfer | 5 days | 2021 September 08 08:00 | 2021 September 15 08:00 | 56SF |  | 3
53 | Yes | Auto Scheduled | Plasmid Assay Development & Qualification | 30 days | 2021 July 21 08:00 | 2021 September 01 08:00 | 54SF |  | 3
54 | Yes | Auto Scheduled | Rep/cap GMP Manufacturing | 15 days | 2021 September 01 08:00 | 2021 September 21 16:00 | 48SS+30d |  | 3
55 | Yes | Auto Scheduled | Rep/cap Analytical Testing | 30 days | 2021 September 22 08:00 | 2021 November 02 16:00 | 54 |  | 3
56 | Yes | Auto Scheduled | Transgene GMP Manufacturing | 15 days | 2021 September 15 08:00 | 2021 October 05 16:00 | 54SS+10d |  | 3
57 | Yes | Auto Scheduled | Transgene Analytical Testing | 20 days | 2021 September 15 08:00 | 2021 October 12 16:00 | 56SS |  | 3
58 | Yes | Auto Scheduled | P-Helper GMP Manufacturing | 15 days | 2021 September 29 08:00 | 2021 October 19 16:00 | 56SS+10d |  | 3
59 | Yes | Auto Scheduled | P-Helper Analytical Testing | 30 days | 2021 September 29 08:00 | 2021 November 09 16:00 | 58SS |  | 3
60 | Yes | Auto Scheduled | Development for RegTox & FIH | 788 days | 2021 January 01 08:00 | 2024 January 09 16:00 |  |  | 2
61 | Yes | Auto Scheduled | Small Scale Evaluation | 20 days | 2021 April 28 08:00 | 2021 May 25 16:00 |  |  | 3
62 | Yes | Auto Scheduled | Plasmid Ratio Evaluation | 20 days | 2021 April 28 08:00 | 2021 May 25 16:00 | 38SS |  | 4
63 | Yes | Auto Scheduled | Downstream 260/280 Evaluation using Tecan | 10 days | 2021 May 12 08:00 | 2021 May 25 16:00 | 62SS+10d |  | 4
64 | Yes | Auto Scheduled | Process Development and Prep of TS | 788 days | 2021 January 01 08:00 | 2024 January 09 16:00 |  |  | 3
65 | Yes | Auto Scheduled | Plasmids for Development | 0 days | 2021 April 28 08:00 | 2021 April 28 08:00 | 62SS |  | 4
66 | Yes | Auto Scheduled | Upstream Process Development (AMBR & 1L) | 100 days | 2021 May 26 08:00 | 2021 October 12 16:00 | 62 |  | 4
67 | Yes | Auto Scheduled | Downstream Process Development | 100 days | 2021 June 16 08:00 | 2021 November 02 16:00 | 66SS+15d |  | 4
68 | Yes | Auto Scheduled | Assay Development (Familiar Capsid) (TS0) | 30 days | 2021 April 28 08:00 | 2021 June 08 16:00 | 38 |  | 4
69 | Yes | Auto Scheduled | Assay Development (Novel Capsid) (TS0) | 45 days | 2021 April 28 08:00 | 2021 June 29 16:00 | 38 |  | 4
70 | Yes | Auto Scheduled | TS1 Candidate: Upstream and Downstream Production (5 x 10L Runs) | 100 days | 2021 May 26 08:00 | 2021 October 12 16:00 | 62 |  | 4
71 | Yes | Auto Scheduled | TS1a Available | 0 days | 2021 June 22 16:00 | 2021 June 22 16:00 | 70SS+20d |  | 4
72 | Yes | Auto Scheduled | TS1b Available | 0 days | 2021 July 20 16:00 | 2021 July 20 16:00 | 71SS+20d |  | 4
73 | Yes | Auto Scheduled | TS1c Available | 0 days | 2021 August 17 16:00 | 2021 August 17 16:00 | 72SS+20d |  | 4
74 | Yes | Auto Scheduled | TS1d Available | 0 days | 2021 September 14 16:00 | 2021 September 14 16:00 | 73SS+20d |  | 4
75 | Yes | Auto Scheduled | TS1e Available | 0 days | 2021 October 12 16:00 | 2021 October 12 16:00 | 74SS+20d |  | 4
76 | Yes | Auto Scheduled | Analytical Support for P1 process development | 35 days | 2021 October 13 08:00 | 2021 November 30 16:00 | 70 |  | 4
77 | Yes | Auto Scheduled | Pre-screen of methods suitability (TS1) | 15 days | 2021 October 13 08:00 | 2021 November 02 16:00 | 70 |  | 4
78 | Yes | Auto Scheduled | Tech Transfer to Pilot Plan (TS2) | 40 days | 2021 October 06 08:00 | 2021 November 30 16:00 |  |  | 4
79 | Yes | Auto Scheduled | Upstream Tech Transfer | 20 days | 2021 October 06 08:00 | 2021 November 02 16:00 | 75FS-5d |  | 5
80 | Yes | Auto Scheduled | Downstream Tech Transfer | 20 days | 2021 November 03 08:00 | 2021 November 30 16:00 | 79 |  | 5
81 | Yes | Auto Scheduled | TS2 Candidate/Process Demo: Upstream and Downstream Production | 20 days | 2021 December 01 08:00 | 2021 December 28 16:00 | 80 |  | 4
82 | Yes | Auto Scheduled | TS2 Candidate: process confirmation in PPD | 20 days | 2021 December 29 08:00 | 2022 January 25 16:00 | 81 |  | 4
83 | Yes | Auto Scheduled | Backup TS2 | 20 days | 2021 December 15 08:00 | 2022 January 11 16:00 | 81SS+10d |  | 4
84 | Yes | Auto Scheduled | Decision Point: Is Process Sufficient to Supply Ph1 Clinical Demand? | 1 day | 2021 December 29 08:00 | 2021 December 29 16:00 | 81 |  | 4
85 | Yes | Auto Scheduled | Candidate formulation evaluation & characterization mAb | 55 days | 2021 December 29 08:00 | 2022 March 15 16:00 | 81 |  | 4
86 | Yes | Auto Scheduled | Method Qualification (TS2) | 65 days | 2021 December 29 08:00 | 2022 March 29 16:00 | 81 |  | 4
87 | Yes | Auto Scheduled | Developmental DP stability (PhRD) using TS2 (24 mo study) | 525 days | 2022 January 05 08:00 | 2024 January 09 16:00 |  |  | 4
88 | Yes | Auto Scheduled | non GMP Stability Study - Start Point | 5 days | 2022 January 05 08:00 | 2022 January 11 16:00 | 81FS+5d |  | 5
89 | Yes | Auto Scheduled | non GMP Stability Study - 1 month pull point | 5 days | 2022 February 04 08:00 | 2022 February 10 16:00 | 88SS+22d |  | 5
90 | Yes | Auto Scheduled | non GMP Stability Study - 2 month pull point | 5 days | 2022 March 08 08:00 | 2022 March 14 16:00 | 88SS+44d |  | 5
91 | Yes | Auto Scheduled | non GMP Stability Study - 3 month pull point | 5 days | 2022 April 06 08:00 | 2022 April 12 16:00 | 88SS+65d |  | 5
92 | Yes | Auto Scheduled | non GMP Stability Study - 6 month pull point | 5 days | 2022 July 06 08:00 | 2022 July 12 16:00 | 88SS+130d |  | 5
93 | Yes | Auto Scheduled | non GMP Stability Study - 9 month pull point | 5 days | 2022 October 05 08:00 | 2022 October 11 16:00 | 88SS+195d |  | 5
94 | Yes | Auto Scheduled | non GMP Stability Study - 12 month pull point | 5 days | 2023 January 04 08:00 | 2023 January 10 16:00 | 88SS+260d |  | 5
95 | Yes | Auto Scheduled | non GMP Stability Study - 18 month pull point | 5 days | 2023 July 05 08:00 | 2023 July 11 16:00 | 88SS+390d |  | 5
96 | Yes | Auto Scheduled | non GMP Stability Study - 24 month pull point | 5 days | 2024 January 03 08:00 | 2024 January 09 16:00 | 88SS+520d |  | 5
97 | Yes | Auto Scheduled | DP Development | 504 days | 2021 January 01 08:00 | 2022 December 07 16:00 |  |  | 4
98 | Yes | Auto Scheduled | Pre-Formulation Development | 44 days | 2021 April 28 08:00 | 2021 June 28 16:00 | 38 |  | 5
99 | Yes | Auto Scheduled | DP Process Development | 44 days | 2021 June 29 08:00 | 2021 August 27 16:00 | 98 |  | 5
100 | Yes | Auto Scheduled | Solution Properties | 66 days | 2021 August 18 08:00 | 2021 November 17 16:00 | 73 |  | 5
101 | Yes | Auto Scheduled | Formulation & Process Nomination/RegTox Handling | 66 days | 2021 January 01 08:00 | 2021 April 02 16:00 |  |  | 5
102 | Yes | Auto Scheduled | Pre-DAI | 44 days | 2021 December 29 08:00 | 2022 February 28 16:00 | 81 |  | 5
103 | Yes | Auto Scheduled | Formulation Development | 66 days | 2021 December 29 08:00 | 2022 March 30 16:00 | 81 |  | 5
104 | Yes | Auto Scheduled | Dosage Administration Instructions (DAI) | 90 days | 2022 August 04 08:00 | 2022 December 07 16:00 | 106FS+30d |  | 5
105 | Yes | Auto Scheduled | Formulation Definition Memo for RegTox and Clinical DS and DP | 0 days | 2022 March 16 16:00 | 2022 March 16 16:00 | 99,88SS+51d,85 |  | 4
106 | Yes | Auto Scheduled | Receive Tox batch 1 material & prep for Preformal and DAI | 0 days | 2022 June 22 16:00 | 2022 June 22 16:00 | 137 |  | 4
107 | Yes | Auto Scheduled | Analytical support for DAI | 90 days | 2022 August 04 08:00 | 2022 December 07 16:00 | 104SS |  | 4
108 | Yes | Auto Scheduled | micro method qualification endo; bio sterility | 20 days | 2022 July 22 08:00 | 2022 August 18 16:00 | 156 |  | 4
109 | Yes | Auto Scheduled | Early Clinical Engagement Meeting 1 (ECE1) | 1 day | 2022 July 11 08:00 | 2022 July 11 16:00 | 141 |  | 4
110 | Yes | Auto Scheduled | Early Clinical Engagement Meeting 2 (ECE2) | 1 day | 2022 October 27 08:00 | 2022 October 27 16:00 | 104SS+60d |  | 4
111 | Yes | Auto Scheduled | Early Clinical Engagement Meeting 3 (ECE3) | 1 day | 2023 January 09 08:00 | 2023 January 09 16:00 | 104FS+22d |  | 4
112 | Yes | Auto Scheduled | Manufacture for RegTox | 796 days | 2021 August 12 08:00 | 2024 August 29 16:00 |  |  | 2
113 | Yes | Auto Scheduled | Tech Transfer to Pilot Plant (RegTox) | 25 days | 2021 December 30 08:00 | 2022 February 02 16:00 |  |  | 3
114 | Yes | Auto Scheduled | Tech transfer USP to Pilot Plant | 10 days | 2021 December 30 08:00 | 2022 January 12 16:00 | 81,84 |  | 4
115 | Yes | Auto Scheduled | Tech Transfer DSP to Pilot Plant | 10 days | 2022 January 20 08:00 | 2022 February 02 16:00 | 114FS+5d |  | 4
116 | Yes | Auto Scheduled | preparation of Reg Tox Specifications | 20 days | 2022 January 13 08:00 | 2022 February 09 16:00 | 121SS |  | 3
117 | Yes | Auto Scheduled | Raws for Reg Tox | 1 day | 2022 August 19 08:00 | 2022 August 19 16:00 | 156FS+20d |  | 3
118 | Yes | Auto Scheduled | Plasmids for Reg Tox (Aldevron) | 66 days | 2021 August 12 08:00 | 2021 November 12 08:00 | 121SF-44d |  | 3
119 | Yes | Auto Scheduled | RegTox Manufacturing Campaign | 180 days | 2022 January 13 08:00 | 2022 September 21 16:00 |  |  | 3
120 | Yes | Auto Scheduled | RegTox Sublots 1-5 | 85 days | 2022 January 13 08:00 | 2022 May 11 16:00 |  |  | 4
121 | Yes | Auto Scheduled | Manufacture RegTox Sublot 1 | 25 days | 2022 January 13 08:00 | 2022 February 16 16:00 | 114 |  | 5
122 | Yes | Auto Scheduled | RegTox Sublot 1 Tier 1 Testing | 20 days | 2022 February 17 08:00 | 2022 March 16 16:00 | 121 |  | 5
123 | Yes | Auto Scheduled | Manufacture RegTox Sublot 2 | 25 days | 2022 January 27 08:00 | 2022 March 02 16:00 | 121SS+10d |  | 5
124 | Yes | Auto Scheduled | RegTox Sublot 2 Tier 1 Testing | 20 days | 2022 March 03 08:00 | 2022 March 30 16:00 | 123 |  | 5
125 | Yes | Auto Scheduled | Manufacture RegTox Sublot 3 | 25 days | 2022 February 10 08:00 | 2022 March 16 16:00 | 123SS+10d |  | 5
126 | Yes | Auto Scheduled | RegTox Sublot 3 Tier 1 Testing | 20 days | 2022 March 17 08:00 | 2022 April 13 16:00 | 125 |  | 5
127 | Yes | Auto Scheduled | Manufacture RegTox Sublot 4 | 25 days | 2022 February 24 08:00 | 2022 March 30 16:00 | 125SS+10d |  | 5
128 | Yes | Auto Scheduled | RegTox Sublot 4 Tier 1 Testing | 20 days | 2022 March 31 08:00 | 2022 April 27 16:00 | 127 |  | 5
129 | Yes | Auto Scheduled | Manufacture RegTox Sublot 5 | 25 days | 2022 March 10 08:00 | 2022 April 13 16:00 | 127SS+10d |  | 5
130 | Yes | Auto Scheduled | RegTox Sublot 5 Tier 1 Testing | 20 days | 2022 April 14 08:00 | 2022 May 11 16:00 | 129 |  | 5
131 | Yes | Auto Scheduled | Reg Tox DS Batch 1 | 105 days | 2022 February 17 08:00 | 2022 July 13 16:00 |  |  | 4
132 | Yes | Auto Scheduled | RegTox (Sublots) Tier 1 Testing Complete | 0 days | 2022 May 11 16:00 | 2022 May 11 16:00 | 130,128,122,126,124 |  | 5
133 | Yes | Auto Scheduled | RegTox DS Batch 1 Mfg | 1 day | 2022 May 12 08:00 | 2022 May 12 16:00 | 132 |  | 5
134 | Yes | Auto Scheduled | Ship Samples | 1 day | 2022 May 13 08:00 | 2022 May 13 16:00 | 133 |  | 5
135 | Yes | Auto Scheduled | Reg Tox Batch 1 (DS) Tier 1 Testing | 20 days | 2022 May 16 08:00 | 2022 June 10 16:00 | 134 |  | 5
136 | Yes | Auto Scheduled | Reg Tox Batch 2 (DS) Release Testing | 40 days | 2022 May 16 08:00 | 2022 July 08 16:00 | 134 |  | 5
137 | Yes | Auto Scheduled | Tox batch 1 Samples to PhRD | 0 days | 2022 June 22 16:00 | 2022 June 22 16:00 | 133SS+30d |  | 5
138 | Yes | Auto Scheduled | Reg Tox Inprocess Sample Testing for information only | 15 days | 2022 February 17 08:00 | 2022 March 09 16:00 | 121 |  | 5
139 | Yes | Auto Scheduled | Reg Tox documentation for DSRD | 20 days | 2022 May 13 08:00 | 2022 June 09 16:00 | 133 |  | 5
140 | Yes | Auto Scheduled | use period- Reg Tox | 5 days | 2022 March 10 08:00 | 2022 March 16 16:00 | 138 |  | 5
141 | Yes | Auto Scheduled | [BTx date] Reg Tox 1 Available (Sublots 1-5) | 0 days | 2022 July 08 16:00 | 2022 July 08 16:00 | 136 |  | 5
142 | Yes | Auto Scheduled | Shipping Reg Tox 1 | 3 days | 2022 July 11 08:00 | 2022 July 13 16:00 | 141 |  | 5
143 | Yes | Auto Scheduled | RegTox Sublots 6-10 | 85 days | 2022 March 24 08:00 | 2022 July 20 16:00 |  |  | 4
144 | Yes | Auto Scheduled | Manufacture RegTox Sublot 6 | 25 days | 2022 March 24 08:00 | 2022 April 27 16:00 | 129SS+10d |  | 5
145 | Yes | Auto Scheduled | RegTox Sublot 6 Tier 1 Testing | 20 days | 2022 April 28 08:00 | 2022 May 25 16:00 | 144 |  | 5
146 | Yes | Auto Scheduled | Manufacture RegTox Sublot 7 | 25 days | 2022 April 07 08:00 | 2022 May 11 16:00 | 144SS+10d |  | 5
147 | Yes | Auto Scheduled | RegTox Sublot 7 Tier 1 Testing | 20 days | 2022 May 12 08:00 | 2022 June 08 16:00 | 146 |  | 5
148 | Yes | Auto Scheduled | Manufacture RegTox Sublot 8 | 25 days | 2022 April 21 08:00 | 2022 May 25 16:00 | 146SS+10d |  | 5
149 | Yes | Auto Scheduled | RegTox Sublot 8 Tier 1 Testing | 20 days | 2022 May 26 08:00 | 2022 June 22 16:00 | 148 |  | 5
150 | Yes | Auto Scheduled | Manufacture RegTox Sublot 9 | 25 days | 2022 May 05 08:00 | 2022 June 08 16:00 | 148SS+10d |  | 5
151 | Yes | Auto Scheduled | RegTox Sublot 9 Tier 1 Testing | 20 days | 2022 June 09 08:00 | 2022 July 06 16:00 | 150 |  | 5
152 | Yes | Auto Scheduled | Manufacture RegTox Sublot 10 | 25 days | 2022 May 19 08:00 | 2022 June 22 16:00 | 150SS+10d |  | 5
153 | Yes | Auto Scheduled | RegTox Sublot 10 Tier 1 Testing | 20 days | 2022 June 23 08:00 | 2022 July 20 16:00 | 152 |  | 5
154 | Yes | Auto Scheduled | Reg Tox DS Batch 2 | 105 days | 2022 April 28 08:00 | 2022 September 21 16:00 |  |  | 4
155 | Yes | Auto Scheduled | RegTox (Sublots) Tier 1 Testing Complete | 0 days | 2022 July 20 16:00 | 2022 July 20 16:00 | 149,145,147,153,151 |  | 5
156 | Yes | Auto Scheduled | RegTox DS Batch 2 Mfg | 1 day | 2022 July 21 08:00 | 2022 July 21 16:00 | 155 |  | 5
157 | Yes | Auto Scheduled | Ship Samples | 1 day | 2022 July 22 08:00 | 2022 July 22 16:00 | 156 |  | 5
158 | Yes | Auto Scheduled | Reg Tox Batch 2 (DS) Tier 1 Testing | 20 days | 2022 July 25 08:00 | 2022 August 19 16:00 | 157 |  | 5
159 | Yes | Auto Scheduled | Reg Tox Batch 2 (DS) Release Testing | 40 days | 2022 July 25 08:00 | 2022 September 16 16:00 | 157 |  | 5
160 | Yes | Auto Scheduled | Tox batch 2 Samples to PhRD | 0 days | 2022 August 31 16:00 | 2022 August 31 16:00 | 156SS+30d |  | 5
161 | Yes | Auto Scheduled | Reg Tox Inprocess Sample Testing for information only | 15 days | 2022 April 28 08:00 | 2022 May 18 16:00 | 144 |  | 5
162 | Yes | Auto Scheduled | Reg Tox documentation for DSRD | 20 days | 2022 July 22 08:00 | 2022 August 18 16:00 | 156 |  | 5
163 | Yes | Auto Scheduled | use period- Reg Tox | 5 days | 2022 May 19 08:00 | 2022 May 25 16:00 | 161 |  | 5
164 | Yes | Auto Scheduled | [BTx date] Reg Tox 2 Available (Sublots 6-10) | 0 days | 2022 September 16 16:00 | 2022 September 16 16:00 | 159 |  | 5
165 | Yes | Auto Scheduled | Shipping Reg Tox 2 | 3 days | 2022 September 19 08:00 | 2022 September 21 16:00 | 164 |  | 5
166 | Yes | Auto Scheduled | Pre-formal DP stability (PhRD/ARD) using Reg tox (24 mo study) | 540 days | 2022 August 05 08:00 | 2024 August 29 16:00 |  |  | 3
167 | Yes | Auto Scheduled | Pre-formal DP stability (PhRD/ARD) - T0 | 20 days | 2022 August 05 08:00 | 2022 September 01 16:00 | 156FS+10d |  | 4
168 | Yes | Auto Scheduled | Pre-formal DP stability (PhRD/ARD) - 1 month pull point | 20 days | 2022 September 06 08:00 | 2022 October 03 16:00 | 167SS+22d |  | 4
169 | Yes | Auto Scheduled | Pre-formal DP stability (PhRD/ARD) - 3 month pull point | 20 days | 2022 November 04 08:00 | 2022 December 01 16:00 | 167SS+65d |  | 4
170 | Yes | Auto Scheduled | Pre-formal DP stability (PhRD/ARD) - 6 month pull point | 20 days | 2023 February 03 08:00 | 2023 March 02 16:00 | 167SS+130d |  | 4
171 | Yes | Auto Scheduled | Pre-formal DP stability (PhRD/ARD) - 9 month pull point | 20 days | 2023 May 05 08:00 | 2023 June 01 16:00 | 167SS+195d |  | 4
172 | Yes | Auto Scheduled | Pre-formal DP stability (PhRD/ARD) - 12 month pull point | 20 days | 2023 August 04 08:00 | 2023 August 31 16:00 | 167SS+260d |  | 4
173 | Yes | Auto Scheduled | Pre-formal DP stability (PhRD/ARD) - 18 month pull point | 20 days | 2024 February 02 08:00 | 2024 February 29 16:00 | 167SS+390d |  | 4
174 | Yes | Auto Scheduled | Pre-formal DP stability (PhRD/ARD) - 24 month pull point | 20 days | 2024 August 02 08:00 | 2024 August 29 16:00 | 167SS+520d |  | 4
175 | Yes | Auto Scheduled | Reference Material | 40 days | 2022 July 22 08:00 | 2022 September 15 16:00 |  |  | 3
176 | Yes | Auto Scheduled | Reference material Vialing/label/Storage/Uniformity Testing | 10 days | 2022 July 22 08:00 | 2022 August 04 16:00 | 156 |  | 4
177 | Yes | Auto Scheduled | Reference material characterization | 30 days | 2022 August 05 08:00 | 2022 September 15 16:00 | 176 |  | 4
178 | Yes | Auto Scheduled | Manufacture for FIH | 601 days | 2022 April 15 08:00 | 2024 August 02 16:00 |  |  | 2
179 | Yes | Auto Scheduled | GMP DS Manufacture | 322 days | 2022 April 15 08:00 | 2023 July 10 16:00 |  |  | 3
180 | Yes | Auto Scheduled | GMP DS Tech Transfer | 61 days | 2022 April 15 08:00 | 2022 July 11 08:00 | 191SF |  | 4
181 | Yes | Auto Scheduled | GMP DS & DP Specifications development & approval | 40 days | 2022 April 15 08:00 | 2022 June 09 16:00 | 180SS |  | 4
182 | Yes | Auto Scheduled | Method verification of DS platform methods | 20 days | 2022 May 16 08:00 | 2022 June 10 16:00 | 135SS |  | 4
183 | Yes | Auto Scheduled | Plasmids on Site Prior to Manufacture | 20 days | 2022 May 30 08:00 | 2022 June 24 16:00 | 191SS-30d |  | 4
184 | Yes | Auto Scheduled | Overhead for GMP-s Plasmid Mfg (ACMF) | 45 days | 2022 May 09 08:00 | 2022 July 11 08:00 | 189SF |  | 4
185 | Yes | Auto Scheduled | Raw Materials for GMP-s Plasmid Mfg (ACMF) | 1 day | 2022 June 13 08:00 | 2022 June 13 16:00 | 191SS-20d |  | 4
186 | Yes | Auto Scheduled | Overhead for GMP DS Mfg (DCMF) | 130 days | 2022 July 11 08:00 | 2023 January 06 16:00 | 189SS |  | 4
187 | Yes | Auto Scheduled | Raws for GMP DS Mfg | 1 day | 2022 June 13 08:00 | 2022 June 13 16:00 | 191SS-20d |  | 4
188 | Yes | Auto Scheduled | Ph1 DS Manufacture (10 sublots @ 250L) | 115 days | 2022 July 11 08:00 | 2022 December 16 16:00 | 191SS |  | 4
189 | Yes | Auto Scheduled | DS Manufacture | 261 days | 2022 July 11 08:00 | 2023 July 10 16:00 |  |  | 4
190 | Yes | Auto Scheduled | DS Sublots 1-5 | 85 days | 2022 July 11 08:00 | 2022 November 04 16:00 |  |  | 5
191 | Yes | Auto Scheduled | DS Sublot 1 Mfg | 25 days | 2022 July 11 08:00 | 2022 August 12 16:00 | 136 |  | 6
192 | Yes | Auto Scheduled | DS Sublot 1 Tier 1 Testing | 20 days | 2022 August 15 08:00 | 2022 September 09 16:00 | 191 |  | 6
193 | Yes | Auto Scheduled | DS Sublot 2 Mfg | 25 days | 2022 July 25 08:00 | 2022 August 26 16:00 | 191SS+10d |  | 6
194 | Yes | Auto Scheduled | DS Sublot 2 Tier 1 Testing | 20 days | 2022 August 29 08:00 | 2022 September 23 16:00 | 193 |  | 6
195 | Yes | Auto Scheduled | DS Sublot 3 Mfg | 25 days | 2022 August 08 08:00 | 2022 September 09 16:00 | 193SS+10d |  | 6
196 | Yes | Auto Scheduled | DS Sublot 3 Tier 1 Testing | 20 days | 2022 September 12 08:00 | 2022 October 07 16:00 | 195 |  | 6
197 | Yes | Auto Scheduled | DS Sublot 4 Mfg | 25 days | 2022 August 22 08:00 | 2022 September 23 16:00 | 195SS+10d |  | 6
198 | Yes | Auto Scheduled | DS Sublot 4 Tier 1 Testing | 20 days | 2022 September 26 08:00 | 2022 October 21 16:00 | 197 |  | 6
199 | Yes | Auto Scheduled | DS Sublot 5 Mfg | 25 days | 2022 September 05 08:00 | 2022 October 07 16:00 | 197SS+10d |  | 6
200 | Yes | Auto Scheduled | DS Sublot 5 Tier 1 Testing | 20 days | 2022 October 10 08:00 | 2022 November 04 16:00 | 199 |  | 6
201 | Yes | Auto Scheduled | DS Batch 1 | 61 days | 2022 November 04 16:00 | 2023 January 30 16:00 |  |  | 5
202 | Yes | Auto Scheduled | Batch 1 Sublots Tier 1 Testing Complete | 0 days | 2022 November 04 16:00 | 2022 November 04 16:00 | 196,198,200,192,194 |  | 6
203 | Yes | Auto Scheduled | DS Batch 1 Mfg | 1 day | 2022 November 07 08:00 | 2022 November 07 16:00 | 202 |  | 6
204 | Yes | Auto Scheduled | GMP DS Release Testing (Batch 1) | 50 days | 2022 November 08 08:00 | 2023 January 16 16:00 | 203 |  | 6
205 | Yes | Auto Scheduled | Bulk Harvest testing (Batch 1) | 40 days | 2022 November 14 08:00 | 2023 January 06 16:00 | 199FS+25d |  | 6
206 | Yes | Auto Scheduled | use period- DS | 5 days | 2023 January 17 08:00 | 2023 January 23 16:00 | 204 |  | 6
207 | Yes | Auto Scheduled | DS inprocess support information only testing | 25 days | 2022 November 08 08:00 | 2022 December 12 16:00 | 203 |  | 6
208 | Yes | Auto Scheduled | Final Disposition GMP DS batch 1 | 10 days | 2023 January 17 08:00 | 2023 January 30 16:00 | 204,205 |  | 6
209 | Yes | Auto Scheduled | DS Sublots 6-10 | 85 days | 2022 September 19 08:00 | 2023 January 13 16:00 |  |  | 5
210 | Yes | Auto Scheduled | DS Sublot 6 Mfg | 25 days | 2022 September 19 08:00 | 2022 October 21 16:00 | 199SS+10d |  | 6
211 | Yes | Auto Scheduled | DS Sublot 6 Tier 1 Testing | 20 days | 2022 October 24 08:00 | 2022 November 18 16:00 | 210 |  | 6
212 | Yes | Auto Scheduled | DS Sublot 7 Mfg | 25 days | 2022 October 03 08:00 | 2022 November 04 16:00 | 210SS+10d |  | 6
213 | Yes | Auto Scheduled | DS Sublot 7 Tier 1 Testing | 20 days | 2022 November 07 08:00 | 2022 December 02 16:00 | 212 |  | 6
214 | Yes | Auto Scheduled | DS Sublot 8 Mfg | 25 days | 2022 October 17 08:00 | 2022 November 18 16:00 | 212SS+10d |  | 6
215 | Yes | Auto Scheduled | DS Sublot 8 Tier 1 Testing | 20 days | 2022 November 21 08:00 | 2022 December 16 16:00 | 214 |  | 6
216 | Yes | Auto Scheduled | DS Sublot 9 Mfg | 25 days | 2022 October 31 08:00 | 2022 December 02 16:00 | 214SS+10d |  | 6
217 | Yes | Auto Scheduled | DS Sublot 9 Tier 1 Testing | 20 days | 2022 December 05 08:00 | 2022 December 30 16:00 | 216 |  | 6
218 | Yes | Auto Scheduled | DS Sublot 10 Mfg | 25 days | 2022 November 14 08:00 | 2022 December 16 16:00 | 216SS+10d |  | 6
219 | Yes | Auto Scheduled | DS Sublot 10 Tier 1 Testing | 20 days | 2022 December 19 08:00 | 2023 January 13 16:00 | 218 |  | 6
220 | Yes | Auto Scheduled | DS Batch 2 | 126 days | 2023 January 13 16:00 | 2023 July 10 16:00 |  |  | 5
221 | Yes | Auto Scheduled | Batch 2 Sublots Tier 1 Testing Complete | 0 days | 2023 January 13 16:00 | 2023 January 13 16:00 | 211,217,213,215,219 |  | 6
222 | Yes | Auto Scheduled | DS Batch 2 Mfg | 1 day | 2023 January 16 08:00 | 2023 January 16 16:00 | 221 |  | 6
223 | Yes | Auto Scheduled | GMP DS Release Testing (Batch 2) | 50 days | 2023 January 17 08:00 | 2023 March 27 16:00 | 222 |  | 6
224 | Yes | Auto Scheduled | Bulk Harvest testing (Batch 2) | 40 days | 2023 May 02 08:00 | 2023 June 26 16:00 | 223FS+25d |  | 6
225 | Yes | Auto Scheduled | DS inprocess support information only testing | 25 days | 2023 January 17 08:00 | 2023 February 20 16:00 | 222 |  | 6
226 | Yes | Auto Scheduled | Final Disposition GMP DS Batch 2 | 10 days | 2023 June 27 08:00 | 2023 July 10 16:00 | 223,224 |  | 6
227 | Yes | Auto Scheduled | GMP DS Analytical Support/Additional Characterization | 192 days | 2022 May 16 08:00 | 2023 February 07 16:00 |  |  | 4
228 | Yes | Auto Scheduled | Sequencing Method (ID & Qualify) | 65 days | 2022 August 10 08:00 | 2022 November 08 16:00 | 191SS+22d |  | 5
229 | Yes | Auto Scheduled | Sequencing Placeholder | 130 days | 2022 August 10 08:00 | 2023 February 07 16:00 | 191SS+22d |  | 5
230 | Yes | Auto Scheduled | Plasmid Receipt ID Testing | 130 days | 2022 May 16 08:00 | 2022 November 11 16:00 | 191SS-40d |  | 5
231 | Yes | Auto Scheduled | rcAAV Testing | 40 days | 2022 August 10 08:00 | 2022 October 04 16:00 | 191SS+22d |  | 5
232 | Yes | Auto Scheduled | DNA Sequencing | 84 days | 2022 August 08 08:00 | 2022 December 01 16:00 | 191SS+20d |  | 5
233 | Yes | Auto Scheduled | Sterility | 40 days | 2022 August 10 08:00 | 2022 October 04 16:00 | 191SS+22d |  | 5
234 | Yes | Auto Scheduled | Affinity Ligand Kits | 1 day | 2022 August 10 08:00 | 2022 August 10 16:00 | 191SS+22d |  | 5
235 | Yes | Auto Scheduled | Benzonase Kits | 1 day | 2022 August 10 08:00 | 2022 August 10 16:00 | 191SS+22d |  | 5
236 | Yes | Auto Scheduled | HCP Kits | 1 day | 2022 August 10 08:00 | 2022 August 10 16:00 | 191SS+22d |  | 5
237 | Yes | Auto Scheduled | DNA Kits | 1 day | 2022 August 10 08:00 | 2022 August 10 16:00 | 191SS+22d |  | 5
238 | Yes | Auto Scheduled | Capsid Titer Kits | 1 day | 2022 August 10 08:00 | 2022 August 10 16:00 | 191SS+22d |  | 5
239 | Yes | Auto Scheduled | Adenovirus E1A DNA Detection | 76 days | 2022 August 10 08:00 | 2022 November 23 16:00 | 191SS+22d |  | 5
240 | Yes | Auto Scheduled | GMP DP Manufacture; Pack & Label for Ph. 1 | 514 days | 2022 August 16 08:00 | 2024 August 02 16:00 |  |  | 3
241 | Yes | Auto Scheduled | Tech Transfer DP | 60 days | 2022 August 16 08:00 | 2022 November 07 16:00 | 247SS-60d,105 |  | 4
242 | Yes | Auto Scheduled | Tech Transfer DP Inprocess Methods | 30 days | 2022 September 28 08:00 | 2022 November 08 16:00 | 247FF |  | 4
243 | Yes | Auto Scheduled | micro method qualification endo; bio sterility | 20 days | 2022 November 09 08:00 | 2022 December 06 16:00 | 251SS |  | 4
244 | Yes | Auto Scheduled | use period- DP | 5 days | 2023 February 01 08:00 | 2023 February 07 16:00 | 251 |  | 4
245 | Yes | Auto Scheduled | Drug Product 1 | 454 days | 2022 November 08 08:00 | 2024 August 02 16:00 |  |  | 4
246 | Yes | Auto Scheduled | Drug Product 1 Manufacturing | 2 days | 2022 November 08 08:00 | 2022 November 09 16:00 |  |  | 5
247 | Yes | Auto Scheduled | DP Mfg 1 (Form and Fill) | 1 day | 2022 November 08 08:00 | 2022 November 08 16:00 | 203 |  | 6
248 | Yes | Auto Scheduled | Inspect & Primary Label | 1 day | 2022 November 09 08:00 | 2022 November 09 16:00 | 247 |  | 6
249 | Yes | Auto Scheduled | Assays to Enable Shipping to Secondary Pack Label (Sterility/Conc) | 20 days | 2022 November 10 08:00 | 2022 December 07 16:00 | 248 |  | 5
250 | Yes | Auto Scheduled | Batch Record Review to Enable Shipping to Secondary Pack Label | 20 days | 2022 November 10 08:00 | 2022 December 07 16:00 | 249SS |  | 5
251 | Yes | Auto Scheduled | Final Assays to Release | 60 days | 2022 November 09 08:00 | 2023 January 31 16:00 | 247 |  | 5
252 | Yes | Auto Scheduled | Disposition of Primary Labeled Vials | 10 days | 2023 February 01 08:00 | 2023 February 14 16:00 | 208,251 |  | 5
253 | Yes | Auto Scheduled | Primary Labeled Vials Tested & Released | 0 days | 2023 February 14 16:00 | 2023 February 14 16:00 | 252 |  | 5
254 | Yes | Auto Scheduled | Ship and Receive DP at Pack/Label Site | 10 days | 2023 February 01 08:00 | 2023 February 14 16:00 | 251 |  | 5
255 | Yes | Auto Scheduled | Just in Time Readiness | 5 days | 2023 February 15 08:00 | 2023 February 21 16:00 | 252 |  | 5
256 | Yes | Auto Scheduled | Release on Approval (ROA) | 2 days | 2023 May 04 08:00 | 2023 May 05 16:00 | 255SS,367 |  | 5
257 | Yes | Auto Scheduled | CTM Available (for further labeling for patients) | 0 days | 2023 May 05 16:00 | 2023 May 05 16:00 | 256 |  | 5
258 | Yes | Auto Scheduled | First IIP Approval | 0 days | 2023 May 01 16:00 | 2023 May 01 16:00 | 366 |  | 5
259 | Yes | Auto Scheduled | First Site Activation | 10 days | 2023 May 08 08:00 | 2023 May 19 16:00 | 256,258 |  | 5
260 | Yes | Auto Scheduled | Patient Screening (FSFV) | 40 days | 2023 May 22 08:00 | 2023 July 14 16:00 | 259 |  | 5
261 | Yes | Auto Scheduled | On Demand Secondary Labeling | 10 days | 2023 July 17 08:00 | 2023 July 28 16:00 | 367,260,257 |  | 5
262 | Yes | Auto Scheduled | Ship DP to Clinical Site | 5 days | 2023 July 31 08:00 | 2023 August 04 16:00 | 261,256 |  | 5
263 | Yes | Auto Scheduled | Clinical Supplies at Site(s) | 0 days | 2023 August 04 16:00 | 2023 August 04 16:00 | 262 |  | 5
264 | Yes | Auto Scheduled | Storage & Distribution | 260 days | 2023 August 07 08:00 | 2024 August 02 16:00 | 263 |  | 5
265 | Yes | Auto Scheduled | Drug Product 2 | 144 days | 2023 January 17 08:00 | 2023 August 04 16:00 |  |  | 4
266 | Yes | Auto Scheduled | Drug Product 2 Manufacturing | 2 days | 2023 January 17 08:00 | 2023 January 18 16:00 |  |  | 5
267 | Yes | Auto Scheduled | DP Mfg 2 (Form and Fill) | 1 day | 2023 January 17 08:00 | 2023 January 17 16:00 | 222 |  | 6
268 | Yes | Auto Scheduled | Inspect & Primary Label | 1 day | 2023 January 18 08:00 | 2023 January 18 16:00 | 267 |  | 6
269 | Yes | Auto Scheduled | Assays to Enable Shipping to Secondary Pack Label (Endotoxin/Conc) | 20 days | 2023 January 19 08:00 | 2023 February 15 16:00 | 268 |  | 5
270 | Yes | Auto Scheduled | Batch Record Review to Enable Shipping to Secondary Pack Label | 20 days | 2023 January 19 08:00 | 2023 February 15 16:00 | 269SS |  | 5
271 | Yes | Auto Scheduled | Final Assays to Release | 60 days | 2023 January 18 08:00 | 2023 April 11 16:00 | 267 |  | 5
272 | Yes | Auto Scheduled | Ship and Receive DP at Pack/Label Site | 10 days | 2023 April 12 08:00 | 2023 April 25 16:00 | 271 |  | 5
273 | Yes | Auto Scheduled | Disposition of Primary Labeled Vials | 10 days | 2023 April 12 08:00 | 2023 April 25 16:00 | 271 |  | 5
274 | Yes | Auto Scheduled | Primary Labeled Vials Tested & Released | 0 days | 2023 April 25 16:00 | 2023 April 25 16:00 | 273 |  | 5
275 | Yes | Auto Scheduled | CTM Available (for further labeling for patients) | 0 days | 2023 May 05 16:00 | 2023 May 05 16:00 | 256,273 |  | 5
276 | Yes | Auto Scheduled | On Demand Secondary Labeling | 10 days | 2023 July 17 08:00 | 2023 July 28 16:00 | 260,275 |  | 5
277 | Yes | Auto Scheduled | Ship DP to Clinical Site | 5 days | 2023 July 31 08:00 | 2023 August 04 16:00 | 276 |  | 5
278 | Yes | Auto Scheduled | Clinical Supplies at Site(s) | 0 days | 2023 August 04 16:00 | 2023 August 04 16:00 | 277 |  | 5
279 | Yes | Auto Scheduled | SC Planning; Pack & Label for Phase 1 | 347 days | 2022 December 08 08:00 | 2024 April 05 16:00 |  |  | 3
280 | Yes | Auto Scheduled | IP Manual | 10 days | 2022 December 08 08:00 | 2022 December 21 16:00 | 104 |  | 4
281 | Yes | Auto Scheduled | Package & Label DP | 30 days | 2023 February 22 08:00 | 2023 April 04 16:00 | 282 |  | 4
282 | Yes | Auto Scheduled | CSA/CPR Approval | 10 days | 2023 February 08 08:00 | 2023 February 21 16:00 | 254FF+5d |  | 4
283 | Yes | Auto Scheduled | IRT Development | 10 days | 2023 February 08 08:00 | 2023 February 21 16:00 | 282SS |  | 4
284 | Yes | Auto Scheduled | Clinical defines countries for Phase 1 | 0 days | 2023 February 08 08:00 | 2023 February 08 08:00 | 282SS |  | 4
285 | Yes | Auto Scheduled | QA release | 3 days | 2023 April 05 08:00 | 2023 April 07 16:00 | 280,281,252,24 |  | 4
286 | Yes | Auto Scheduled | Storage & Distribution | 260 days | 2023 April 10 08:00 | 2024 April 05 16:00 | 285 |  | 4
287 | Yes | Auto Scheduled | IRT Activation | 5 days | 2023 April 10 08:00 | 2023 April 14 16:00 | 285 |  | 4
288 | Yes | Auto Scheduled | Stability Testing for RegTox & FIH | 1646 days | 2022 February 17 08:00 | 2028 June 08 16:00 |  |  | 2
289 | Yes | Auto Scheduled | Reg Tox DS stability (in QC/Stability lab) (12 mo + 24 mo contingency sample) | 280 days | 2022 February 17 08:00 | 2023 March 15 16:00 |  |  | 3
290 | Yes | Auto Scheduled | non GMP Stability Study (Reg Tox) - Start Point | 20 days | 2022 February 17 08:00 | 2022 March 16 16:00 | 121 |  | 4
291 | Yes | Auto Scheduled | non GMP Stability Study (Reg Tox) - 3 month pull point | 20 days | 2022 May 19 08:00 | 2022 June 15 16:00 | 290SS+65d |  | 4
292 | Yes | Auto Scheduled | non GMP Stability Study (Reg Tox) - 6 month pull point | 20 days | 2022 August 18 08:00 | 2022 September 14 16:00 | 290SS+130d |  | 4
293 | Yes | Auto Scheduled | non GMP Stability Study (Reg Tox) - 9 month pull point | 20 days | 2022 November 17 08:00 | 2022 December 14 16:00 | 290SS+195d |  | 4
294 | Yes | Auto Scheduled | non GMP Stability Study (Reg Tox) - 12 month pull point | 20 days | 2023 February 16 08:00 | 2023 March 15 16:00 | 290SS+260d |  | 4
295 | Yes | Auto Scheduled | non GMP Stability Study (Reg Tox) - 18 month pull point | 20 days | 2022 November 17 08:00 | 2022 December 14 16:00 | 290SS+195d |  | 4
296 | Yes | Auto Scheduled | non GMP Stability Study (Reg Tox) - 24 month pull point | 20 days | 2023 February 16 08:00 | 2023 March 15 16:00 | 290SS+260d |  | 4
297 | Yes | Auto Scheduled | Reference Material DS Stability | 1561 days | 2022 June 16 08:00 | 2028 June 08 16:00 |  |  | 3
298 | Yes | Auto Scheduled | RM Stability Study- Start Point | 1 day | 2022 June 16 08:00 | 2022 June 16 16:00 | 161FS+20d |  | 4
299 | Yes | Auto Scheduled | RM Stability Study- 12 month pull point | 1 day | 2023 June 15 08:00 | 2023 June 15 16:00 | 298SS+260d |  | 4
300 | Yes | Auto Scheduled | RM Stability Study- 24 month pull point | 1 day | 2024 June 13 08:00 | 2024 June 13 16:00 | 298SS+520d |  | 4
301 | Yes | Auto Scheduled | RM Stability Study- 36 month pull point | 1 day | 2025 June 12 08:00 | 2025 June 12 16:00 | 298SS+780d |  | 4
302 | Yes | Auto Scheduled | RM Stability Study- 48 month pull point | 1 day | 2026 June 11 08:00 | 2026 June 11 16:00 | 298SS+1040d |  | 4
303 | Yes | Auto Scheduled | RM Stability Study- 60 month pull point | 1 day | 2027 June 10 08:00 | 2027 June 10 16:00 | 298SS+1300d |  | 4
304 | Yes | Auto Scheduled | RM Stability Study- 72 month pull point | 1 day | 2028 June 08 08:00 | 2028 June 08 16:00 | 298SS+1560d |  | 4
305 | Yes | Auto Scheduled | GMP Drug Substance Stability (48 mo) | 1101 days | 2022 September 13 08:00 | 2026 December 01 16:00 |  |  | 3
306 | Yes | Auto Scheduled | method transfer complete and approved | 50 days | 2022 September 13 08:00 | 2022 November 22 08:00 | 308SF-10d |  | 4
307 | Yes | Auto Scheduled | Stability Initiation; Admin Support | 30 days | 2022 October 25 08:00 | 2022 December 06 08:00 | 308SF |  | 4
308 | Yes | Auto Scheduled | DS Stability Study - Start Point | 1 day | 2022 December 06 08:00 | 2022 December 06 16:00 | 203FS+20d |  | 4
309 | Yes | Auto Scheduled | DS Stability Study - 1 month pull point | 1 day | 2023 January 05 08:00 | 2023 January 05 16:00 | 308SS+22d |  | 4
310 | Yes | Auto Scheduled | DS Stability Study - 3 month pull point | 1 day | 2023 March 07 08:00 | 2023 March 07 16:00 | 308SS+65d |  | 4
311 | Yes | Auto Scheduled | DS Stability Study - 6 month pull point | 1 day | 2023 June 06 08:00 | 2023 June 06 16:00 | 308SS+130d |  | 4
312 | Yes | Auto Scheduled | DS Stability Study - 9 month pull point | 1 day | 2023 September 05 08:00 | 2023 September 05 16:00 | 308SS+195d |  | 4
313 | Yes | Auto Scheduled | DS Stability Study - 12 month pull point | 1 day | 2023 December 05 08:00 | 2023 December 05 16:00 | 308SS+260d |  | 4
314 | Yes | Auto Scheduled | DS Stability Study - 18 month pull point | 1 day | 2024 June 04 08:00 | 2024 June 04 16:00 | 308SS+390d |  | 4
315 | Yes | Auto Scheduled | DS Stability Study - 24 month pull point | 1 day | 2024 December 03 08:00 | 2024 December 03 16:00 | 308SS+520d |  | 4
316 | Yes | Auto Scheduled | DS Stability Study - 30 month pull point | 1 day | 2025 June 03 08:00 | 2025 June 03 16:00 | 308SS+650d |  | 4
317 | Yes | Auto Scheduled | DS Stability Study - 36 month pull point | 1 day | 2025 December 02 08:00 | 2025 December 02 16:00 | 308SS+780d |  | 4
318 | Yes | Auto Scheduled | DS Stability Study - 42 month pull point | 1 day | 2026 June 02 08:00 | 2026 June 02 16:00 | 308SS+910d |  | 4
319 | Yes | Auto Scheduled | DS Stability Study - 48 month pull point | 1 day | 2026 December 01 08:00 | 2026 December 01 16:00 | 308SS+1040d |  | 4
320 | Yes | Auto Scheduled | GMP Drug Product Stability (48 mo) | 1101 days | 2022 September 28 08:00 | 2026 December 16 16:00 |  |  | 3
321 | Yes | Auto Scheduled | method transfer complete and approved | 50 days | 2022 September 28 08:00 | 2022 December 07 08:00 | 323SF-10d |  | 4
322 | Yes | Auto Scheduled | Stability Initiation; Admin Support | 30 days | 2022 November 09 08:00 | 2022 December 21 08:00 | 323SF |  | 4
323 | Yes | Auto Scheduled | DP Stability Study - Start Point | 1 day | 2022 December 21 08:00 | 2022 December 21 16:00 | 247FS+30d |  | 4
324 | Yes | Auto Scheduled | DP Stability Study - 1 month pull point | 1 day | 2023 January 20 08:00 | 2023 January 20 16:00 | 323SS+22d |  | 4
325 | Yes | Auto Scheduled | DP Stability Study - 3 month pull point | 1 day | 2023 March 22 08:00 | 2023 March 22 16:00 | 323SS+65d |  | 4
326 | Yes | Auto Scheduled | DP Stability Study - 6 month pull point | 1 day | 2023 June 21 08:00 | 2023 June 21 16:00 | 323SS+130d |  | 4
327 | Yes | Auto Scheduled | DP Stability Study - 9 month pull point | 1 day | 2023 September 20 08:00 | 2023 September 20 16:00 | 323SS+195d |  | 4
328 | Yes | Auto Scheduled | DP Stability Study - 12 month pull point | 1 day | 2023 December 20 08:00 | 2023 December 20 16:00 | 323SS+260d |  | 4
329 | Yes | Auto Scheduled | DP Stability Study - 18 month pull point | 1 day | 2024 June 19 08:00 | 2024 June 19 16:00 | 323SS+390d |  | 4
330 | Yes | Auto Scheduled | DP Stability Study - 24 month pull point | 1 day | 2024 December 18 08:00 | 2024 December 18 16:00 | 323SS+520d |  | 4
331 | Yes | Auto Scheduled | DP Stability Study - 30 month pull point | 1 day | 2025 June 18 08:00 | 2025 June 18 16:00 | 323SS+650d |  | 4
332 | Yes | Auto Scheduled | DP Stability Study - 36 month pull point | 1 day | 2025 December 17 08:00 | 2025 December 17 16:00 | 323SS+780d |  | 4
333 | Yes | Auto Scheduled | DP Stability Study - 42 month pull point | 1 day | 2026 June 17 08:00 | 2026 June 17 16:00 | 323SS+910d |  | 4
334 | Yes | Auto Scheduled | DP Stability Study - 48 month pull point | 1 day | 2026 December 16 08:00 | 2026 December 16 16:00 | 323SS+1040d |  | 4
335 | Yes | Auto Scheduled | Regulatory Documentation and Filing for IND/IMPD/CTX (File on RegTox) | 472 days | 2021 July 13 08:00 | 2023 May 03 16:00 |  |  | 2
336 | Yes | Auto Scheduled | On-going CMC documentation and strategy for FIH | 375 days | 2021 July 13 08:00 | 2022 December 19 16:00 | 358FF |  | 3
337 | Yes | Auto Scheduled | Health Authority Meeting Prep for FIH (eg. Pre-IND/IMPD) | 130 days | 2021 December 21 08:00 | 2022 June 20 16:00 | 358FF-130d |  | 3
338 | Yes | Auto Scheduled | Author & review CMC sections for IND/IMPD | 254 days | 2022 May 13 08:00 | 2023 May 03 16:00 |  |  | 3
339 | Yes | Auto Scheduled | IND Kickoff Meeting | 1 day | 2022 May 13 08:00 | 2022 May 13 16:00 | 159FF-90d |  | 4
340 | Yes | Auto Scheduled | Draft A | 81 days | 2022 May 16 08:00 | 2022 September 05 16:00 |  |  | 4
341 | Yes | Auto Scheduled | Drafts due from authors | 40 days | 2022 May 16 08:00 | 2022 July 08 16:00 | 339 |  | 5
342 | Yes | Auto Scheduled | GCMC Compiles Draft A fo review | 1 day | 2022 July 11 08:00 | 2022 July 11 16:00 | 341 |  | 5
343 | Yes | Auto Scheduled | Draft A Team Review | 5 days | 2022 July 12 08:00 | 2022 July 18 16:00 | 342 |  | 5
344 | Yes | Auto Scheduled | Data verification SOP-REG-00456 | 35 days | 2022 July 19 08:00 | 2022 September 05 16:00 | 343 |  | 5
345 | Yes | Auto Scheduled | Draft B | 20 days | 2022 October 04 08:00 | 2022 October 31 16:00 |  |  | 4
346 | Yes | Auto Scheduled | Draft B GCMC Compilation of Draft Filing | 5 days | 2022 October 04 08:00 | 2022 October 10 16:00 | 159,168 |  | 5
347 | Yes | Auto Scheduled | Draft B Cross Functional Review (includes PSPT and Line Mgt.) | 5 days | 2022 October 11 08:00 | 2022 October 17 16:00 | 346 |  | 5
348 | Yes | Auto Scheduled | Draft B Comment Review Meeting | 0 days | 2022 October 17 16:00 | 2022 October 17 16:00 | 347 |  | 5
349 | Yes | Auto Scheduled | Authors update (SOP Reg 00456 start data verification) | 10 days | 2022 October 18 08:00 | 2022 October 31 16:00 | 348 |  | 5
350 | Yes | Auto Scheduled | Draft C | 6 days | 2022 November 01 08:00 | 2022 November 08 16:00 |  |  | 4
351 | Yes | Auto Scheduled | Draft C GCMC Compilation of Draft Filing | 1 day | 2022 November 01 08:00 | 2022 November 01 16:00 | 349 |  | 5
352 | Yes | Auto Scheduled | Draft C Cross Functional Line Review (includes PSPT and Line Mgt.) | 2 days | 2022 November 02 08:00 | 2022 November 03 16:00 | 351 |  | 5
353 | Yes | Auto Scheduled | Authors Update SOP Reg 00456 & data verification complete | 3 days | 2022 November 04 08:00 | 2022 November 08 16:00 | 352 |  | 5
354 | Yes | Auto Scheduled | IND Cross Functional Line Approval | 3 days | 2022 November 09 08:00 | 2022 November 11 16:00 | 353 |  | 4
355 | Yes | Auto Scheduled | Publishing and Submission Activities | 25 days | 2022 November 14 08:00 | 2022 December 16 16:00 |  |  | 4
356 | Yes | Auto Scheduled | RCM Publishing Activities | 20 days | 2022 November 14 08:00 | 2022 December 09 16:00 | 354 |  | 5
357 | Yes | Auto Scheduled | Hand-off to WRS Operations | 5 days | 2022 December 12 08:00 | 2022 December 16 16:00 | 356 |  | 5
358 | Yes | Auto Scheduled | Submission to FDA by WRS Operations | 1 day | 2022 December 19 08:00 | 2022 December 19 16:00 | 357 |  | 4
359 | Yes | Auto Scheduled | 6 Week Review Period | 30 days | 2022 December 20 08:00 | 2023 January 30 16:00 | 358 |  | 4
360 | Yes | Auto Scheduled | PDM Update After Review Period | 3 days | 2023 January 31 08:00 | 2023 February 02 16:00 | 359 |  | 4
361 | Yes | Auto Scheduled | QA/RoA Release in US (Follows IND Wait & PDM Update) | 2 days | 2023 February 03 08:00 | 2023 February 06 16:00 | 360 |  | 4
362 | Yes | Auto Scheduled | IND Amendment (GMP Data) | 66 days | 2023 February 01 08:00 | 2023 May 03 16:00 |  |  | 4
363 | Yes | Auto Scheduled | Author IND Amendment | 30 days | 2023 February 01 08:00 | 2023 March 14 16:00 | 251 |  | 5
364 | Yes | Auto Scheduled | Submission of Amendment to FDA by WRS Operations | 1 day | 2023 March 15 08:00 | 2023 March 15 16:00 | 363 |  | 5
365 | Yes | Auto Scheduled | 6 Week Review Period (Amendment) | 30 days | 2023 March 16 08:00 | 2023 April 26 16:00 | 364 |  | 5
366 | Yes | Auto Scheduled | PDM Update After Review Period (Amendment) | 3 days | 2023 April 27 08:00 | 2023 May 01 16:00 | 365 |  | 5
367 | Yes | Auto Scheduled | QA/RoA Release (Amendment) in US (Follows IND Wait & PDM Update) | 2 days | 2023 May 02 08:00 | 2023 May 03 16:00 | 366 |  | 5
368 | Yes | Auto Scheduled | PharmSci BioTx mAb FIH-POC | 495 days | 2025 May 26 08:00 | 2027 April 16 16:00 |  |  | 1
369 | Yes | Auto Scheduled | WWRA IND/IMPD Collate & Publishing | 10 days | 2025 May 26 08:00 | 2025 June 06 16:00 | 403FS+10d |  | 2
370 | Yes | Auto Scheduled | IND/IMPD Amendment for P2 | 0 days | 2025 June 06 16:00 | 2025 June 06 16:00 | 369 |  | 2
371 | Yes | Auto Scheduled | Regulatory Review | 22 days | 2025 June 09 08:00 | 2025 July 08 16:00 | 370 |  | 2
372 | Yes | Auto Scheduled | [BTx date] Phase 2a/b Start | 0 days | 2025 August 29 16:00 | 2025 August 29 16:00 | 371,33FS+269d |  | 2
373 | Yes | Auto Scheduled | Phase 2a/b | 420 days | 2025 September 08 08:00 | 2027 April 16 16:00 | 372,417 |  | 2
374 | Yes | Auto Scheduled | Development and Manufacture P2ED | 1639 days | 2023 January 25 08:00 | 2029 May 07 16:00 |  |  | 1
375 | Yes | Auto Scheduled | Team Activities - Phase 1 | 540 days | 2023 August 04 16:00 | 2025 August 29 16:00 |  |  | 2
376 | Yes | Auto Scheduled | PS BTx Start Trigger | 0 days | 2023 August 04 16:00 | 2023 August 04 16:00 | 31 |  | 3
377 | Yes | Auto Scheduled | PS BTx End Trigger | 0 days | 2025 August 29 16:00 | 2025 August 29 16:00 | 372 |  | 3
378 | Yes | Auto Scheduled | Development FIH to POC | 520 days | 2023 August 07 08:00 | 2025 August 01 16:00 |  |  | 2
379 | Yes | Auto Scheduled | On-going development work FIH to POC | 520 days | 2023 August 07 08:00 | 2025 August 01 16:00 | 31 |  | 3
380 | Yes | Auto Scheduled | GMP DS Reload | 152 days | 2024 January 22 08:00 | 2024 August 20 16:00 |  |  | 2
381 | Yes | Auto Scheduled | Reload DS Manufacturing | 60 days | 2024 January 22 08:00 | 2024 April 12 16:00 | 191SS+400d |  | 3
382 | Yes | Auto Scheduled | Reload DS Analytical Support/Additional Characterization | 130 days | 2024 February 21 08:00 | 2024 August 20 16:00 |  |  | 3
383 | Yes | Auto Scheduled | Sequencing Placeholder | 130 days | 2024 February 21 08:00 | 2024 August 20 16:00 | 381SS+22d |  | 4
384 | Yes | Auto Scheduled | Plasmid Receipt ID Testing | 130 days | 2024 February 21 08:00 | 2024 August 20 16:00 | 381SS+22d |  | 4
385 | Yes | Auto Scheduled | rcAAV Testing | 40 days | 2024 February 21 08:00 | 2024 April 16 16:00 | 381SS+22d |  | 4
386 | Yes | Auto Scheduled | DNA Sequencing | 84 days | 2024 February 21 08:00 | 2024 June 17 16:00 | 381SS+22d |  | 4
387 | Yes | Auto Scheduled | Sterility | 40 days | 2024 February 21 08:00 | 2024 April 16 16:00 | 381SS+22d |  | 4
388 | Yes | Auto Scheduled | Affinity Ligand Kits | 1 day | 2024 February 21 08:00 | 2024 February 21 16:00 | 381SS+22d |  | 4
389 | Yes | Auto Scheduled | Benzonase Kits | 1 day | 2024 February 21 08:00 | 2024 February 21 16:00 | 381SS+22d |  | 4
390 | Yes | Auto Scheduled | HCP Kits | 1 day | 2024 February 21 08:00 | 2024 February 21 16:00 | 381SS+22d |  | 4
391 | Yes | Auto Scheduled | DNA Kits | 1 day | 2024 February 21 08:00 | 2024 February 21 16:00 | 381SS+22d |  | 4
392 | Yes | Auto Scheduled | Capsid Titer Kits | 1 day | 2024 February 21 08:00 | 2024 February 21 16:00 | 381SS+22d |  | 4
393 | Yes | Auto Scheduled | Adenovirus E1A DNA Detection | 76 days | 2024 February 21 08:00 | 2024 June 05 16:00 | 381SS+22d |  | 4
394 | Yes | Auto Scheduled | Overhead for GMP-s Plasmid Mfg for Reload (ACMF) | 0 days | 2024 January 22 08:00 | 2024 January 22 08:00 | 381SF |  | 2
395 | Yes | Auto Scheduled | Raw Materials for GMP-s Plasmids for Reload | 0 days | 2023 December 25 08:00 | 2023 December 25 08:00 | 394SS-20d |  | 2
396 | Yes | Auto Scheduled | Overhead for Reload GMP DS Mfg (DCMF) | 0 days | 2024 January 22 08:00 | 2024 January 22 08:00 | 381SS |  | 2
397 | Yes | Auto Scheduled | Raws for GMP DS Reload | 0 days | 2023 January 25 08:00 | 2023 January 25 08:00 | 281SS-20d |  | 2
398 | Yes | Auto Scheduled | GMP DP Manufacture & Release Testing FIH to POC | 110 days | 2024 December 23 08:00 | 2025 May 23 16:00 |  |  | 2
399 | Yes | Auto Scheduled | Tech Transfer DP to LDM FIH to POC | 60 days | 2024 December 23 08:00 | 2025 March 14 16:00 | 402SS-60d |  | 3
400 | Yes | Auto Scheduled | Tech Transfer DP Inprocess Methods (new Site) | 30 days | 2025 February 17 08:00 | 2025 March 28 16:00 | 402FF |  | 3
401 | Yes | Auto Scheduled | Specifications setting/approval | 10 days | 2025 March 17 08:00 | 2025 March 28 16:00 | 402FF |  | 3
402 | Yes | Auto Scheduled | DP Mfg FIH to POC | 10 days | 2025 March 17 08:00 | 2025 March 28 16:00 | 31FS+420d |  | 3
403 | Yes | Auto Scheduled | GMP DP Release Testing | 30 days | 2025 March 31 08:00 | 2025 May 09 16:00 | 402 |  | 3
404 | Yes | Auto Scheduled | micro method qualification endo; bio sterility | 20 days | 2025 March 31 08:00 | 2025 April 25 16:00 | 403SS |  | 3
405 | Yes | Auto Scheduled | use period- DP | 5 days | 2025 May 12 08:00 | 2025 May 16 16:00 | 403 |  | 3
406 | Yes | Auto Scheduled | Disposition GMP DP FIH to POC | 10 days | 2025 May 12 08:00 | 2025 May 23 16:00 | 403 |  | 3
407 | Yes | Auto Scheduled | SC Planning; Pack & Label for Phase 1 FIH to POC | 85 days | 2025 May 12 08:00 | 2025 September 05 16:00 |  |  | 2
408 | Yes | Auto Scheduled | Clinical defines countries for Phase 2 FIH to POC | 0 days | 2025 May 12 08:00 | 2025 May 12 08:00 | 410SS |  | 3
409 | Yes | Auto Scheduled | Ship DP to pack and label FIH to POC | 10 days | 2025 May 12 08:00 | 2025 May 23 16:00 | 403 |  | 3
410 | Yes | Auto Scheduled | CSA/CPR Approval FIH to POC | 10 days | 2025 May 12 08:00 | 2025 May 23 16:00 | 409FF |  | 3
411 | Yes | Auto Scheduled | IRT Development | 10 days | 2025 May 12 08:00 | 2025 May 23 16:00 | 410SS |  | 3
412 | Yes | Auto Scheduled | Package & Label DP FIH to POC | 50 days | 2025 May 26 08:00 | 2025 August 01 16:00 | 410 |  | 3
413 | Yes | Auto Scheduled | QA release (RoA)/QP release FIH to POC | 10 days | 2025 August 04 08:00 | 2025 August 15 16:00 | 412,406 |  | 3
414 | Yes | Auto Scheduled | Site Activation | 10 days | 2025 August 11 08:00 | 2025 August 25 08:00 | 416SF |  | 3
415 | Yes | Auto Scheduled | IRT Activation | 5 days | 2025 August 18 08:00 | 2025 August 22 16:00 | 413 |  | 3
416 | Yes | Auto Scheduled | Ship DP to Clinical site FIH to POC | 10 days | 2025 August 25 08:00 | 2025 September 05 16:00 | 413,415 |  | 3
417 | Yes | Auto Scheduled | Clinical Supplies at the Site(s) | 0 days | 2025 September 05 16:00 | 2025 September 05 16:00 | 416 |  | 3
418 | Yes | Auto Scheduled | Regulatory Documentation FIH-POC | 480 days | 2023 August 07 08:00 | 2025 June 06 16:00 |  |  | 2
419 | Yes | Auto Scheduled | On-going CMC documentation and strategy for P2 | 480 days | 2023 August 07 08:00 | 2025 June 06 16:00 |  |  | 3
420 | Yes | Auto Scheduled | BTx Trigger Start | 0 days | 2023 August 07 08:00 | 2023 August 07 08:00 | 379SS |  | 4
421 | Yes | Auto Scheduled | BTx Trigger End | 0 days | 2025 June 06 16:00 | 2025 June 06 16:00 | 423FF |  | 4
422 | Yes | Auto Scheduled | Health Authority Meeting Prep for P2 (eg. Pre-IND; EOP2; Scientific Advice (SA)) | 130 days | 2024 September 09 08:00 | 2025 March 07 16:00 | 373SS-260d |  | 3
423 | Yes | Auto Scheduled | Author & review CMC sections for P2 IND/IMPD Amendment | 60 days | 2025 March 17 08:00 | 2025 June 06 16:00 | 403FF+10d,406FF+10d |  | 3
424 | Yes | Auto Scheduled | GMP Drug Product Stability (48 mo) | 1101 days | 2025 February 17 08:00 | 2029 May 07 16:00 |  |  | 2
425 | Yes | Auto Scheduled | method transfer complete and approved | 50 days | 2025 February 17 08:00 | 2025 April 28 08:00 | 427SF-10d |  | 3
426 | Yes | Auto Scheduled | Stability Initiation; Admin Support | 30 days | 2025 March 31 08:00 | 2025 May 12 08:00 | 427SF |  | 3
427 | Yes | Auto Scheduled | DP Stability Study - Start Point | 1 day | 2025 May 12 08:00 | 2025 May 12 16:00 | 402FS+30d |  | 3
428 | Yes | Auto Scheduled | DP Stability Study - 1 month pull point | 1 day | 2025 June 11 08:00 | 2025 June 11 16:00 | 427SS+22d |  | 3
429 | Yes | Auto Scheduled | DP Stability Study - 3 month pull point | 1 day | 2025 August 11 08:00 | 2025 August 11 16:00 | 427SS+65d |  | 3
430 | Yes | Auto Scheduled | DP Stability Study - 6 month pull point | 1 day | 2025 November 10 08:00 | 2025 November 10 16:00 | 427SS+130d |  | 3
431 | Yes | Auto Scheduled | DP Stability Study - 9 month pull point | 1 day | 2026 February 09 08:00 | 2026 February 09 16:00 | 427SS+195d |  | 3
432 | Yes | Auto Scheduled | DP Stability Study - 12 month pull point | 1 day | 2026 May 11 08:00 | 2026 May 11 16:00 | 427SS+260d |  | 3
433 | Yes | Auto Scheduled | DP Stability Study - 18 month pull point | 1 day | 2026 November 09 08:00 | 2026 November 09 16:00 | 427SS+390d |  | 3
434 | Yes | Auto Scheduled | DP Stability Study - 24 month pull point | 1 day | 2027 May 10 08:00 | 2027 May 10 16:00 | 427SS+520d |  | 3
435 | Yes | Auto Scheduled | DP Stability Study - 30 month pull point | 1 day | 2027 November 08 08:00 | 2027 November 08 16:00 | 427SS+650d |  | 3
436 | Yes | Auto Scheduled | DP Stability Study - 36 month pull point | 1 day | 2028 May 08 08:00 | 2028 May 08 16:00 | 427SS+780d |  | 3
437 | Yes | Auto Scheduled | DP Stability Study - 42 month pull point | 1 day | 2028 November 06 08:00 | 2028 November 06 16:00 | 427SS+910d |  | 3
438 | Yes | Auto Scheduled | DP Stability Study - 48 month pull point | 1 day | 2029 May 07 08:00 | 2029 May 07 16:00 | 427SS+1040d |  | 3
439 | Yes | Auto Scheduled | Manufacture P2FD | 1836 days | 2025 January 13 08:00 | 2032 January 26 16:00 |  |  | 1
440 | Yes | Auto Scheduled | Team Activities - Phase 2a/b | 571 days | 2025 August 29 16:00 | 2027 November 08 16:00 |  |  | 2
441 | Yes | Auto Scheduled | PS BTx Start Trigger | 0 days | 2025 August 29 16:00 | 2025 August 29 16:00 | 372 |  | 3
442 | Yes | Auto Scheduled | PS BTx End Trigger | 0 days | 2027 November 08 16:00 | 2027 November 08 16:00 | 592 |  | 3
443 | Yes | Auto Scheduled | P3 Readiness Meeting | 0 days | 2025 January 13 08:00 | 2025 January 13 08:00 | 583SS-260d |  | 2
444 | Yes | Auto Scheduled | CoDev Transition Meeting | 0 days | 2025 July 14 08:00 | 2025 July 14 08:00 | 583SS-130d |  | 2
445 | Yes | Auto Scheduled | Evaluate strategic options for supply TS3 mAb material | 0 days | 2025 July 14 08:00 | 2025 July 14 08:00 | 583SS-130d |  | 2
446 | Yes | Auto Scheduled | Evaluate commercial suitability of MCB | 130 days | 2025 July 14 08:00 | 2026 January 09 16:00 | 583SS-130d |  | 2
447 | Yes | Auto Scheduled | Identify strategy for mfg TS4 mAb material (includes CMO options) | 0 days | 2026 January 12 08:00 | 2026 January 12 08:00 | 583 |  | 2
448 | Yes | Auto Scheduled | CoDev Kickoff Meeting | 0 days | 2026 February 06 16:00 | 2026 February 06 16:00 | 583FF+20d |  | 2
449 | Yes | Auto Scheduled | Manufacture P2FD | 465 days | 2026 August 17 08:00 | 2028 May 26 16:00 |  |  | 2
450 | Yes | Auto Scheduled | GMP DS Manufacture & Release Testing FIH to POC | 152 days | 2026 August 17 08:00 | 2027 March 16 16:00 |  |  | 3
451 | Yes | Auto Scheduled | Evaluate need to source TS3 from DS Reload | 0 days | 2026 August 17 08:00 | 2026 August 17 08:00 | 452SS-10d |  | 4
452 | Yes | Auto Scheduled | Tech Transfer FIH to POC | 40 days | 2026 August 31 08:00 | 2026 October 23 16:00 | 31SS+800d |  | 4
453 | Yes | Auto Scheduled | Raws for GMP Mfg FIH to POC | 1 day | 2026 September 28 08:00 | 2026 September 28 16:00 | 454SS-20d |  | 4
454 | Yes | Auto Scheduled | DS Manufacture FIH to POC | 40 days | 2026 October 26 08:00 | 2026 December 18 16:00 | 452 |  | 4
455 | Yes | Auto Scheduled | Specifications setting/approval | 10 days | 2026 November 10 08:00 | 2026 November 23 16:00 | 456FF |  | 4
456 | Yes | Auto Scheduled | Resins for GMP Mfg FIH to POC | 1 day | 2026 November 23 08:00 | 2026 November 23 16:00 | 454SS+20d |  | 4
457 | Yes | Auto Scheduled | Resin Topoff | 1 day | 2026 November 23 08:00 | 2026 November 23 16:00 | 456SS |  | 4
458 | Yes | Auto Scheduled | Bulk Harvest testing FIH to POC (Batch 1) | 40 days | 2026 November 30 08:00 | 2027 January 22 16:00 | 454SS+25d |  | 4
459 | Yes | Auto Scheduled | GMP DS Release Testing (Batch 1) | 20 days | 2026 December 07 08:00 | 2027 January 01 16:00 | 454SS+30d |  | 4
460 | Yes | Auto Scheduled | micro method qualification endo; bio sterility | 20 days | 2026 December 07 08:00 | 2027 January 01 16:00 | 459SS |  | 4
461 | Yes | Auto Scheduled | use period- DS | 5 days | 2027 January 04 08:00 | 2027 January 08 16:00 | 459 |  | 4
462 | Yes | Auto Scheduled | Bulk Harvest testing FIH to POC (Batch 2-3) | 40 days | 2026 December 14 08:00 | 2027 February 05 16:00 | 454FS-5d |  | 4
463 | Yes | Auto Scheduled | GMP DS Release Testing (Batch 2-3) | 20 days | 2026 December 21 08:00 | 2027 January 15 16:00 | 454 |  | 4
464 | Yes | Auto Scheduled | DS inprocess support information only testing | 25 days | 2026 December 21 08:00 | 2027 January 22 16:00 | 454 |  | 4
465 | Yes | Auto Scheduled | DS Comparibility | 30 days | 2026 December 21 08:00 | 2027 January 29 16:00 |  |  | 4
466 | Yes | Auto Scheduled | GMP DS Comparability- Primary Structure | 30 days | 2026 December 21 08:00 | 2027 January 29 16:00 | 454 |  | 5
467 | Yes | Auto Scheduled | GMP DS Comparability- Post-translational Modifications | 30 days | 2026 December 21 08:00 | 2027 January 29 16:00 | 454 |  | 5
468 | Yes | Auto Scheduled | GMP DS Comparability- Product Isoforms/Degradation Products/Impurities | 30 days | 2026 December 21 08:00 | 2027 January 29 16:00 | 454 |  | 5
469 | Yes | Auto Scheduled | GMP DS Comparability- Higher Order Structure | 30 days | 2026 December 21 08:00 | 2027 January 29 16:00 | 454 |  | 5
470 | Yes | Auto Scheduled | GMP DS Comparability- Biological Activity | 30 days | 2026 December 21 08:00 | 2027 January 29 16:00 | 454 |  | 5
471 | Yes | Auto Scheduled | Interim Release GMP DS batch 1 | 10 days | 2027 January 04 08:00 | 2027 January 15 16:00 | 459 |  | 4
472 | Yes | Auto Scheduled | Ship & Receive DS to DP CMO or LDM FIH to POC | 10 days | 2027 January 18 08:00 | 2027 January 29 16:00 | 471 |  | 4
473 | Yes | Auto Scheduled | DS IPC Testing | 42 days | 2027 January 18 08:00 | 2027 March 16 16:00 | 454FS+20d |  | 4
474 | Yes | Auto Scheduled | Final Disposition GMP DS batch 1 | 10 days | 2027 January 25 08:00 | 2027 February 05 16:00 | 459,458 |  | 4
475 | Yes | Auto Scheduled | GMP DP Manufacture & Release Testing FIH to POC | 120 days | 2026 October 26 08:00 | 2027 April 09 16:00 |  |  | 3
476 | Yes | Auto Scheduled | Tech Transfer DP to LDM FIH to POC | 60 days | 2026 October 26 08:00 | 2027 January 15 16:00 | 483SS-70d |  | 4
477 | Yes | Auto Scheduled | Tech Transfer DP Inprocess Methods (new Site) | 30 days | 2027 January 04 08:00 | 2027 February 12 16:00 | 483FF |  | 4
478 | Yes | Auto Scheduled | Pbo Mfg | 10 days | 2027 January 18 08:00 | 2027 January 29 16:00 | 483SS-10d |  | 4
479 | Yes | Auto Scheduled | PBO Release Testing | 30 days | 2027 February 01 08:00 | 2027 March 12 16:00 | 478 |  | 4
480 | Yes | Auto Scheduled | micro method qualification endo; bio sterility | 20 days | 2027 February 01 08:00 | 2027 February 26 16:00 | 479SS |  | 4
481 | Yes | Auto Scheduled | use period- DP | 5 days | 2027 March 15 08:00 | 2027 March 19 16:00 | 479 |  | 4
482 | Yes | Auto Scheduled | Specifications setting/approval | 10 days | 2027 February 01 08:00 | 2027 February 12 16:00 | 483FF |  | 4
483 | Yes | Auto Scheduled | DP Mfg FIH to POC | 10 days | 2027 February 01 08:00 | 2027 February 12 16:00 | 471,472 |  | 4
484 | Yes | Auto Scheduled | GMP DP Release Testing | 30 days | 2027 February 15 08:00 | 2027 March 26 16:00 | 483 |  | 4
485 | Yes | Auto Scheduled | micro method qualification endo; bio sterility | 20 days | 2027 February 15 08:00 | 2027 March 12 16:00 | 484SS |  | 4
486 | Yes | Auto Scheduled | use period- DP | 5 days | 2027 March 29 08:00 | 2027 April 02 16:00 | 484 |  | 4
487 | Yes | Auto Scheduled | Disposition GMP DP FIH to POC | 10 days | 2027 March 29 08:00 | 2027 April 09 16:00 | 474,484 |  | 4
488 | Yes | Auto Scheduled | SC Planning; Pack & Label for Phase 1 FIH to POC | 85 days | 2027 March 29 08:00 | 2027 July 23 16:00 |  |  | 3
489 | Yes | Auto Scheduled | Clinical confirms country(ies) and study design | 0 days | 2027 March 29 08:00 | 2027 March 29 08:00 | 492SS |  | 4
490 | Yes | Auto Scheduled | Ship DP to pack and label FIH to POC | 10 days | 2027 March 29 08:00 | 2027 April 09 16:00 | 484 |  | 4
491 | Yes | Auto Scheduled | IRT development | 10 days | 2027 March 29 08:00 | 2027 April 09 16:00 | 489 |  | 4
492 | Yes | Auto Scheduled | CSA/CPR Approval FIH to POC | 10 days | 2027 March 29 08:00 | 2027 April 09 16:00 | 490FF |  | 4
493 | Yes | Auto Scheduled | Package & Label DP FIH to POC | 50 days | 2027 April 12 08:00 | 2027 June 18 16:00 | 490,492 |  | 4
494 | Yes | Auto Scheduled | QA release (RoA)/QP release FIH to POC | 10 days | 2027 June 21 08:00 | 2027 July 02 16:00 | 493,491 |  | 4
495 | Yes | Auto Scheduled | Site Activation | 10 days | 2027 June 28 08:00 | 2027 July 12 08:00 | 497SF |  | 4
496 | Yes | Auto Scheduled | IRT activation | 5 days | 2027 July 05 08:00 | 2027 July 09 16:00 | 494 |  | 4
497 | Yes | Auto Scheduled | Ship DP to Clinical site FIH to POC | 10 days | 2027 July 12 08:00 | 2027 July 23 16:00 | 496,370FS+10d,494 |  | 4
498 | Yes | Auto Scheduled | Clinical Supplies at the Site(s) | 0 days | 2027 July 23 16:00 | 2027 July 23 16:00 | 497 |  | 4
499 | Yes | Auto Scheduled | GMP DP Manufacture & Release Testing FIH to POC | 120 days | 2027 August 30 08:00 | 2028 February 11 16:00 |  |  | 3
500 | Yes | Auto Scheduled | Tech Transfer DP to LDM FIH to POC | 60 days | 2027 August 30 08:00 | 2027 November 19 16:00 | 506SS-70d |  | 4
501 | Yes | Auto Scheduled | Tech Transfer DP Inprocess Methods (new Site) | 30 days | 2027 November 08 08:00 | 2027 December 17 16:00 | 506FF |  | 4
502 | Yes | Auto Scheduled | Pbo Mfg | 10 days | 2027 November 22 08:00 | 2027 December 03 16:00 | 506SS-10d |  | 4
503 | Yes | Auto Scheduled | PBO Release Testing | 30 days | 2027 December 06 08:00 | 2028 January 14 16:00 | 502 |  | 4
504 | Yes | Auto Scheduled | micro method qualification endo; bio sterility | 20 days | 2027 December 06 08:00 | 2027 December 31 16:00 | 503SS |  | 4
505 | Yes | Auto Scheduled | use period- DP | 5 days | 2028 January 17 08:00 | 2028 January 21 16:00 | 503 |  | 4
506 | Yes | Auto Scheduled | DP Mfg FIH to POC | 10 days | 2027 December 06 08:00 | 2027 December 17 16:00 | 498FS+95d |  | 4
507 | Yes | Auto Scheduled | Specifications setting/approval | 10 days | 2027 December 06 08:00 | 2027 December 17 16:00 | 506FF |  | 4
508 | Yes | Auto Scheduled | GMP DP Release Testing | 30 days | 2027 December 20 08:00 | 2028 January 28 16:00 | 506 |  | 4
509 | Yes | Auto Scheduled | micro method qualification endo; bio sterility | 20 days | 2027 December 20 08:00 | 2028 January 14 16:00 | 508SS |  | 4
510 | Yes | Auto Scheduled | use period- DP | 5 days | 2028 January 31 08:00 | 2028 February 04 16:00 | 508 |  | 4
511 | Yes | Auto Scheduled | Disposition GMP DP FIH to POC | 10 days | 2028 January 31 08:00 | 2028 February 11 16:00 | 508 |  | 4
512 | Yes | Auto Scheduled | SC Planning; Pack & Label for Phase 1 FIH to POC | 85 days | 2028 January 31 08:00 | 2028 May 26 16:00 |  |  | 3
513 | Yes | Auto Scheduled | Clinical confirms country(ies) and study design | 0 days | 2028 January 31 08:00 | 2028 January 31 08:00 | 516SS |  | 4
514 | Yes | Auto Scheduled | Ship DP to pack and label FIH to POC | 10 days | 2028 January 31 08:00 | 2028 February 11 16:00 | 508 |  | 4
515 | Yes | Auto Scheduled | IRT development | 10 days | 2028 January 31 08:00 | 2028 February 11 16:00 | 513 |  | 4
516 | Yes | Auto Scheduled | CSA/CPR Approval FIH to POC | 10 days | 2028 January 31 08:00 | 2028 February 11 16:00 | 514FF |  | 4
517 | Yes | Auto Scheduled | Package & Label DP FIH to POC | 50 days | 2028 February 14 08:00 | 2028 April 21 16:00 | 514,516 |  | 4
518 | Yes | Auto Scheduled | QA release (RoA)/QP release FIH to POC | 10 days | 2028 April 24 08:00 | 2028 May 05 16:00 | 517,515 |  | 4
519 | Yes | Auto Scheduled | Site Activation | 10 days | 2028 May 01 08:00 | 2028 May 15 08:00 | 521SF |  | 4
520 | Yes | Auto Scheduled | IRT activation | 5 days | 2028 May 08 08:00 | 2028 May 12 16:00 | 518 |  | 4
521 | Yes | Auto Scheduled | Ship DP to Clinical site FIH to POC | 10 days | 2028 May 15 08:00 | 2028 May 26 16:00 | 520,518 |  | 4
522 | Yes | Auto Scheduled | Clinical Supplies at the Site(s) | 0 days | 2028 May 26 16:00 | 2028 May 26 16:00 | 521 |  | 4
523 | Yes | Auto Scheduled | Stability Testing P2FD | 1371 days | 2026 October 26 08:00 | 2032 January 26 16:00 |  |  | 2
524 | Yes | Auto Scheduled | GMP Drug Substance Stability (48 mo) | 1101 days | 2026 October 26 08:00 | 2031 January 13 16:00 |  |  | 3
525 | Yes | Auto Scheduled | method transfer complete and approved. | 50 days | 2026 October 26 08:00 | 2027 January 04 08:00 | 527SF-10d |  | 4
526 | Yes | Auto Scheduled | Stability Initiation; Admin Support | 30 days | 2026 December 07 08:00 | 2027 January 18 08:00 | 527SF |  | 4
527 | Yes | Auto Scheduled | DS Stability Study - Start Point | 1 day | 2027 January 18 08:00 | 2027 January 18 16:00 | 454FS+20d |  | 4
528 | Yes | Auto Scheduled | DS Stability Study - 1 month pull point | 1 day | 2027 February 17 08:00 | 2027 February 17 16:00 | 527SS+22d |  | 4
529 | Yes | Auto Scheduled | DS Stability Study - 3 month pull point | 1 day | 2027 April 19 08:00 | 2027 April 19 16:00 | 527SS+65d |  | 4
530 | Yes | Auto Scheduled | DS Stability Study - 6 month pull point | 1 day | 2027 July 19 08:00 | 2027 July 19 16:00 | 527SS+130d |  | 4
531 | Yes | Auto Scheduled | DS Stability Study - 9 month pull point | 1 day | 2027 October 18 08:00 | 2027 October 18 16:00 | 527SS+195d |  | 4
532 | Yes | Auto Scheduled | DS Stability Study - 12 month pull point | 1 day | 2028 January 17 08:00 | 2028 January 17 16:00 | 527SS+260d |  | 4
533 | Yes | Auto Scheduled | DS Stability Study - 18 month pull point | 1 day | 2028 July 17 08:00 | 2028 July 17 16:00 | 527SS+390d |  | 4
534 | Yes | Auto Scheduled | DS Stability Study - 24 month pull point | 1 day | 2029 January 15 08:00 | 2029 January 15 16:00 | 527SS+520d |  | 4
535 | Yes | Auto Scheduled | DS Stability Study - 30 month pull point | 1 day | 2029 July 16 08:00 | 2029 July 16 16:00 | 527SS+650d |  | 4
536 | Yes | Auto Scheduled | DS Stability Study - 36 month pull point | 1 day | 2030 January 14 08:00 | 2030 January 14 16:00 | 527SS+780d |  | 4
537 | Yes | Auto Scheduled | DS Stability Study - 42 month pull point | 1 day | 2030 July 15 08:00 | 2030 July 15 16:00 | 527SS+910d |  | 4
538 | Yes | Auto Scheduled | DS Stability Study - 48 month pull point | 1 day | 2031 January 13 08:00 | 2031 January 13 16:00 | 527SS+1040d |  | 4
539 | Yes | Auto Scheduled | PBO Stability (outsourced) | 1041 days | 2027 March 15 08:00 | 2031 March 10 16:00 |  |  | 3
540 | Yes | Auto Scheduled | PBO Stability Study - Start Point | 1 day | 2027 March 15 08:00 | 2027 March 15 16:00 | 479 |  | 4
541 | Yes | Auto Scheduled | PBO Stability Study - 1 month pull point | 1 day | 2027 April 14 08:00 | 2027 April 14 16:00 | 540SS+22d |  | 4
542 | Yes | Auto Scheduled | PBO Stability Study - 3 month pull point | 1 day | 2027 June 14 08:00 | 2027 June 14 16:00 | 540SS+65d |  | 4
543 | Yes | Auto Scheduled | PBO Stability Study - 6 month pull point | 1 day | 2027 September 13 08:00 | 2027 September 13 16:00 | 540SS+130d |  | 4
544 | Yes | Auto Scheduled | PBO Stability Study - 9 month pull point | 1 day | 2027 December 13 08:00 | 2027 December 13 16:00 | 540SS+195d |  | 4
545 | Yes | Auto Scheduled | PBO Stability Study - 12 month pull point | 1 day | 2028 March 13 08:00 | 2028 March 13 16:00 | 540SS+260d |  | 4
546 | Yes | Auto Scheduled | PBO Stability Study - 18 month pull point | 1 day | 2028 September 11 08:00 | 2028 September 11 16:00 | 540SS+390d |  | 4
547 | Yes | Auto Scheduled | PBO Stability Study - 24 month pull point | 1 day | 2029 March 12 08:00 | 2029 March 12 16:00 | 540SS+520d |  | 4
548 | Yes | Auto Scheduled | PBO Stability Study - 30 month pull point | 1 day | 2029 September 10 08:00 | 2029 September 10 16:00 | 540SS+650d |  | 4
549 | Yes | Auto Scheduled | PBO Stability Study - 36 month pull point | 1 day | 2030 March 11 08:00 | 2030 March 11 16:00 | 540SS+780d |  | 4
550 | Yes | Auto Scheduled | PBO Stability Study - 42 month pull point | 1 day | 2030 September 09 08:00 | 2030 September 09 16:00 | 540SS+910d |  | 4
551 | Yes | Auto Scheduled | PBO Stability Study - 48 month pull point | 1 day | 2031 March 10 08:00 | 2031 March 10 16:00 | 540SS+1040d |  | 4
552 | Yes | Auto Scheduled | GMP Drug Product Stability (48 mo) | 1101 days | 2027 January 04 08:00 | 2031 March 24 16:00 |  |  | 3
553 | Yes | Auto Scheduled | method transfer complete and approved. | 50 days | 2027 January 04 08:00 | 2027 March 15 08:00 | 555SF-10d |  | 4
554 | Yes | Auto Scheduled | Stability Initiation; Admin Support | 30 days | 2027 February 15 08:00 | 2027 March 29 08:00 | 555SF |  | 4
555 | Yes | Auto Scheduled | DP Stability Study - Start Point | 1 day | 2027 March 29 08:00 | 2027 March 29 16:00 | 483FS+30d |  | 4
556 | Yes | Auto Scheduled | DP Stability Study - 1 month pull point | 1 day | 2027 April 28 08:00 | 2027 April 28 16:00 | 555SS+22d |  | 4
557 | Yes | Auto Scheduled | DP Stability Study - 3 month pull point | 1 day | 2027 June 28 08:00 | 2027 June 28 16:00 | 555SS+65d |  | 4
558 | Yes | Auto Scheduled | DP Stability Study - 6 month pull point | 1 day | 2027 September 27 08:00 | 2027 September 27 16:00 | 555SS+130d |  | 4
559 | Yes | Auto Scheduled | DP Stability Study - 9 month pull point | 1 day | 2027 December 27 08:00 | 2027 December 27 16:00 | 555SS+195d |  | 4
560 | Yes | Auto Scheduled | DP Stability Study - 12 month pull point | 1 day | 2028 March 27 08:00 | 2028 March 27 16:00 | 555SS+260d |  | 4
561 | Yes | Auto Scheduled | DP Stability Study - 18 month pull point | 1 day | 2028 September 25 08:00 | 2028 September 25 16:00 | 555SS+390d |  | 4
562 | Yes | Auto Scheduled | DP Stability Study - 24 month pull point | 1 day | 2029 March 26 08:00 | 2029 March 26 16:00 | 555SS+520d |  | 4
563 | Yes | Auto Scheduled | DP Stability Study - 30 month pull point | 1 day | 2029 September 24 08:00 | 2029 September 24 16:00 | 555SS+650d |  | 4
564 | Yes | Auto Scheduled | DP Stability Study - 36 month pull point | 1 day | 2030 March 25 08:00 | 2030 March 25 16:00 | 555SS+780d |  | 4
565 | Yes | Auto Scheduled | DP Stability Study - 42 month pull point | 1 day | 2030 September 23 08:00 | 2030 September 23 16:00 | 555SS+910d |  | 4
566 | Yes | Auto Scheduled | DP Stability Study - 48 month pull point | 1 day | 2031 March 24 08:00 | 2031 March 24 16:00 | 555SS+1040d |  | 4
567 | Yes | Auto Scheduled | GMP Drug Product Stability (48 mo) | 1101 days | 2027 November 08 08:00 | 2032 January 26 16:00 |  |  | 3
568 | Yes | Auto Scheduled | method transfer complete and approved. | 50 days | 2027 November 08 08:00 | 2028 January 17 08:00 | 570SF-10d |  | 4
569 | Yes | Auto Scheduled | Stability Initiation; Admin Support | 30 days | 2027 December 20 08:00 | 2028 January 31 08:00 | 570SF |  | 4
570 | Yes | Auto Scheduled | DP Stability Study - Start Point | 1 day | 2028 January 31 08:00 | 2028 January 31 16:00 | 506FS+30d |  | 4
571 | Yes | Auto Scheduled | DP Stability Study - 1 month pull point | 1 day | 2028 March 01 08:00 | 2028 March 01 16:00 | 570SS+22d |  | 4
572 | Yes | Auto Scheduled | DP Stability Study - 3 month pull point | 1 day | 2028 May 01 08:00 | 2028 May 01 16:00 | 570SS+65d |  | 4
573 | Yes | Auto Scheduled | DP Stability Study - 6 month pull point | 1 day | 2028 July 31 08:00 | 2028 July 31 16:00 | 570SS+130d |  | 4
574 | Yes | Auto Scheduled | DP Stability Study - 9 month pull point | 1 day | 2028 October 30 08:00 | 2028 October 30 16:00 | 570SS+195d |  | 4
575 | Yes | Auto Scheduled | DP Stability Study - 12 month pull point | 1 day | 2029 January 29 08:00 | 2029 January 29 16:00 | 570SS+260d |  | 4
576 | Yes | Auto Scheduled | DP Stability Study - 18 month pull point | 1 day | 2029 July 30 08:00 | 2029 July 30 16:00 | 570SS+390d |  | 4
577 | Yes | Auto Scheduled | DP Stability Study - 24 month pull point | 1 day | 2030 January 28 08:00 | 2030 January 28 16:00 | 570SS+520d |  | 4
578 | Yes | Auto Scheduled | DP Stability Study - 30 month pull point | 1 day | 2030 July 29 08:00 | 2030 July 29 16:00 | 570SS+650d |  | 4
579 | Yes | Auto Scheduled | DP Stability Study - 36 month pull point | 1 day | 2031 January 27 08:00 | 2031 January 27 16:00 | 570SS+780d |  | 4
580 | Yes | Auto Scheduled | DP Stability Study - 42 month pull point | 1 day | 2031 July 28 08:00 | 2031 July 28 16:00 | 570SS+910d |  | 4
581 | Yes | Auto Scheduled | DP Stability Study - 48 month pull point | 1 day | 2032 January 26 08:00 | 2032 January 26 16:00 | 570SS+1040d |  | 4
582 | Yes | Auto Scheduled | PharmSci BioTx mAb POC-Launch | 1272 days | 2025 December 09 08:00 | 2030 October 23 16:00 |  |  | 1
583 | Yes | Auto Scheduled | PS Commercial Process Development Start | 0 days | 2026 January 12 08:00 | 2026 January 12 08:00 | 373FS-330d |  | 2
584 | Yes | Auto Scheduled | TPP = Target Product Profile Available | 0 days | 2026 January 12 08:00 | 2026 January 12 08:00 | 583FF |  | 2
585 | Yes | Auto Scheduled | Chronic Tox | 260 days | 2026 January 12 08:00 | 2027 January 08 16:00 | 583 |  | 2
586 | Yes | Auto Scheduled | [BTx date] Proof Of Concept-DP1-BU ownership | 20 days | 2027 January 12 08:00 | 2027 February 08 16:00 | 373FF-49d |  | 2
587 | Yes | Auto Scheduled | Reproductive Tox | 320 days | 2027 April 12 08:00 | 2028 June 30 16:00 | 752FS+20d,585SS+325d |  | 2
588 | Yes | Auto Scheduled | WWRA IND Collate & Publishing | 20 days | 2027 September 07 08:00 | 2027 October 04 16:00 | 856 |  | 2
589 | Yes | Auto Scheduled | IND/IMPD Amendment for P3 | 0 days | 2027 October 04 16:00 | 2027 October 04 16:00 | 588 |  | 2
590 | Yes | Auto Scheduled | Regulatory Review | 22 days | 2027 October 05 08:00 | 2027 November 03 16:00 | 589 |  | 2
591 | Yes | Auto Scheduled | Ph 3/Pivotal Siting Decision | 0 days | 2025 December 09 08:00 | 2025 December 09 08:00 | 752SS-260d |  | 2
592 | Yes | Auto Scheduled | [BTx date] Phase 3 Start | 0 days | 2027 November 08 16:00 | 2027 November 08 16:00 | 373FS+146d |  | 2
593 | Yes | Auto Scheduled | Phase 3 | 614 days | 2027 November 16 08:00 | 2030 March 22 16:00 | 801,592 |  | 2
594 | Yes | Auto Scheduled | BLA Submission | 0 days | 2030 October 23 16:00 | 2030 October 23 16:00 | 993FS+34d,593FS+153d,990FS+20d |  | 2
595 | Yes | Auto Scheduled | Development and Manufacture P3/ICH | 1616 days | 2025 May 29 08:00 | 2031 August 07 16:00 |  |  | 1
596 | Yes | Auto Scheduled | Cell Banking | 150 days | 2025 July 14 08:00 | 2026 February 06 16:00 |  |  | 2
597 | Yes | Auto Scheduled | WCB TT | 20 days | 2025 July 14 08:00 | 2025 August 08 16:00 | 598SF+5d |  | 3
598 | Yes | Auto Scheduled | WCB Prep Activities | 40 days | 2025 August 04 08:00 | 2025 September 29 08:00 | 599SF |  | 3
599 | Yes | Auto Scheduled | WCB Manufacture | 15 days | 2025 September 29 08:00 | 2025 October 20 08:00 | 601SF |  | 3
600 | Yes | Auto Scheduled | Cell Bank Environmental Monitoring | 15 days | 2025 September 29 08:00 | 2025 October 17 16:00 | 599SS |  | 3
601 | Yes | Auto Scheduled | WCB Full Release characterization/ testing | 60 days | 2025 October 20 08:00 | 2026 January 12 08:00 | 607SF |  | 3
602 | Yes | Auto Scheduled | WCB Final Documentation | 20 days | 2026 January 12 08:00 | 2026 February 06 16:00 | 601 |  | 3
603 | Yes | Auto Scheduled | Development for CoDev to Phase 3 & Commercial | 1529 days | 2025 September 29 08:00 | 2031 August 07 16:00 |  |  | 2
604 | Yes | Auto Scheduled | Commercial DS Process Devlopment | 711 days | 2026 January 12 08:00 | 2028 October 02 16:00 |  |  | 3
605 | Yes | Auto Scheduled | P3 DS Development | 711 days | 2026 January 12 08:00 | 2028 October 02 16:00 |  |  | 4
606 | Yes | Auto Scheduled | TS3 Available (assume it comes from reload mfg) | 0 days | 2026 January 12 08:00 | 2026 January 12 08:00 | 583 |  | 5
607 | Yes | Auto Scheduled | USP P3 Development | 110 days | 2026 January 12 08:00 | 2026 June 12 16:00 | 583 |  | 5
608 | Yes | Auto Scheduled | DSP P3 Development | 110 days | 2026 February 09 08:00 | 2026 July 10 16:00 | 607SS+20d |  | 5
609 | Yes | Auto Scheduled | USP P3 confirmation & generational age | 20 days | 2026 June 15 08:00 | 2026 July 10 16:00 | 607 |  | 5
610 | Yes | Auto Scheduled | TT to Pilot for P3 Process Demonstration | 16 days | 2026 July 13 08:00 | 2026 August 03 16:00 | 609,607 |  | 5
611 | Yes | Auto Scheduled | P3 Process Demonstration (3 x 500 L) | 50 days | 2026 August 04 08:00 | 2026 October 12 16:00 | 610 |  | 5
612 | Yes | Auto Scheduled | TS4 Available (first Demo batch with no analytical results) | 0 days | 2026 September 14 16:00 | 2026 September 14 16:00 | 611SS+30d |  | 5
613 | Yes | Auto Scheduled | Developmental DS stability (PhRD/ARD) | 530 days | 2026 September 22 08:00 | 2028 October 02 16:00 |  |  | 5
614 | Yes | Auto Scheduled | non GMP Stability Study - Start Point | 1 day | 2026 September 22 08:00 | 2026 September 22 16:00 | 612FS+5d |  | 6
615 | Yes | Auto Scheduled | non GMP Stability Study - 1 month pull point | 10 days | 2026 October 22 08:00 | 2026 November 04 16:00 | 614SS+22d |  | 6
616 | Yes | Auto Scheduled | non GMP Stability Study - 3 month pull point | 10 days | 2026 December 22 08:00 | 2027 January 04 16:00 | 614SS+65d |  | 6
617 | Yes | Auto Scheduled | non GMP Stability Study - 6 month pull point | 10 days | 2027 March 23 08:00 | 2027 April 05 16:00 | 614SS+130d |  | 6
618 | Yes | Auto Scheduled | non GMP Stability Study - 9 month pull point | 10 days | 2027 June 22 08:00 | 2027 July 05 16:00 | 614SS+195d |  | 6
619 | Yes | Auto Scheduled | non GMP Stability Study - 12 month pull point | 10 days | 2027 September 21 08:00 | 2027 October 04 16:00 | 614SS+260d |  | 6
620 | Yes | Auto Scheduled | non GMP Stability Study - 18 month pull point | 10 days | 2028 March 21 08:00 | 2028 April 03 16:00 | 614SS+390d |  | 6
621 | Yes | Auto Scheduled | non GMP Stability Study - 24 month pull point | 10 days | 2028 September 19 08:00 | 2028 October 02 16:00 | 614SS+520d |  | 6
622 | Yes | Auto Scheduled | Commercial Formulation Development | 1454 days | 2026 January 12 08:00 | 2031 August 07 16:00 |  |  | 3
623 | Yes | Auto Scheduled | P3 DP Development | 1454 days | 2026 January 12 08:00 | 2031 August 07 16:00 |  |  | 4
624 | Yes | Auto Scheduled | TPP | 0 days | 2026 January 12 08:00 | 2026 January 12 08:00 | 606 |  | 5
625 | Yes | Auto Scheduled | Customer Facing Meeting (DPP) | 0 days | 2026 January 12 08:00 | 2026 January 12 08:00 | 624 |  | 5
626 | Yes | Auto Scheduled | Formulation Optimization / DOE | 120 days | 2026 January 12 08:00 | 2026 June 26 16:00 | 583,624 |  | 5
627 | Yes | Auto Scheduled | Analytics for Formulation Optimization / DOE | 120 days | 2026 January 12 08:00 | 2026 June 26 16:00 | 626SS |  | 5
628 | Yes | Auto Scheduled | Design Control | 1307 days | 2026 August 05 08:00 | 2031 August 07 16:00 |  |  | 5
629 | Yes | Auto Scheduled | Design Control - Phase 1 | 44 days | 2026 August 05 08:00 | 2026 October 06 08:00 | 625,630SF |  | 6
630 | Yes | Auto Scheduled | Design Control - Phase 2 | 65 days | 2026 October 06 08:00 | 2027 January 05 08:00 | 631SF |  | 6
631 | Yes | Auto Scheduled | Design Control - Phase 3.1 | 65 days | 2027 January 05 08:00 | 2027 April 06 08:00 | 781SF |  | 6
632 | Yes | Auto Scheduled | Design Control - Phase 3.2 (clinical) | 65 days | 2027 March 02 08:00 | 2027 June 01 08:00 | 791SF |  | 6
633 | Yes | Auto Scheduled | Design Control - Phase 3.2 (commercial) | 65 days | 2028 May 11 08:00 | 2028 August 10 08:00 | 988SF |  | 6
634 | Yes | Auto Scheduled | Design Control - Phase 4a | 130 days | 2030 February 27 08:00 | 2030 August 27 16:00 | 993FF |  | 6
635 | Yes | Auto Scheduled | Design Control - Phase 4b | 130 days | 2031 February 07 08:00 | 2031 August 07 16:00 | 996FF |  | 6
636 | Yes | Auto Scheduled | Final QTTP (requires TTP 6 mo earlier) | 0 days | 2026 September 14 16:00 | 2026 September 14 16:00 | 612 |  | 5
637 | Yes | Auto Scheduled | Define Phase 3 / Commercial product and process | 1 day | 2026 November 10 08:00 | 2026 November 10 16:00 | 647,648 |  | 5
638 | Yes | Auto Scheduled | Developmental DP stability (PhRD/ARD) | 530 days | 2026 September 29 08:00 | 2028 October 09 16:00 |  |  | 4
639 | Yes | Auto Scheduled | non GMP Stability Study - Start Point | 1 day | 2026 September 29 08:00 | 2026 September 29 16:00 | 612FS+10d |  | 5
640 | Yes | Auto Scheduled | non GMP Stability Study - 1 month pull point | 10 days | 2026 October 29 08:00 | 2026 November 11 16:00 | 639SS+22d |  | 5
641 | Yes | Auto Scheduled | non GMP Stability Study - 3 month pull point | 10 days | 2026 December 29 08:00 | 2027 January 11 16:00 | 639SS+65d |  | 5
642 | Yes | Auto Scheduled | non GMP Stability Study - 6 month pull point | 10 days | 2027 March 30 08:00 | 2027 April 12 16:00 | 639SS+130d |  | 5
643 | Yes | Auto Scheduled | non GMP Stability Study - 9 month pull point | 10 days | 2027 June 29 08:00 | 2027 July 12 16:00 | 639SS+195d |  | 5
644 | Yes | Auto Scheduled | non GMP Stability Study - 12 month pull point | 10 days | 2027 September 28 08:00 | 2027 October 11 16:00 | 639SS+260d |  | 5
645 | Yes | Auto Scheduled | non GMP Stability Study - 18 month pull point | 10 days | 2028 March 28 08:00 | 2028 April 10 16:00 | 639SS+390d |  | 5
646 | Yes | Auto Scheduled | non GMP Stability Study - 24 month pull point | 10 days | 2028 September 26 08:00 | 2028 October 09 16:00 | 639SS+520d |  | 5
647 | Yes | Auto Scheduled | Process Development supporting Tech Transfer | 95 days | 2026 June 29 08:00 | 2026 November 06 16:00 | 627 |  | 4
648 | Yes | Auto Scheduled | DP Risk assessment #1 | 1 day | 2026 November 09 08:00 | 2026 November 09 16:00 | 647 |  | 4
649 | Yes | Auto Scheduled | DP Mfg Filter Validation (five components) | 260 days | 2027 February 16 08:00 | 2028 February 14 16:00 | 755 |  | 4
650 | Yes | Auto Scheduled | DP E/L Filtrations Process Support | 260 days | 2027 February 16 08:00 | 2028 February 14 16:00 | 649SS |  | 4
651 | Yes | Auto Scheduled | DP Process Filter Flush | 130 days | 2027 February 16 08:00 | 2027 August 16 16:00 | 649SS |  | 4
652 | Yes | Auto Scheduled | Dosage Administration Instructions (CoDev) | 70 days | 2027 April 20 08:00 | 2027 July 26 16:00 | 781 |  | 4
653 | Yes | Auto Scheduled | DAI Support | 10 days | 2027 July 13 08:00 | 2027 July 26 16:00 | 652FF |  | 4
654 | Yes | Auto Scheduled | Device development | 1271 days | 2025 December 15 08:00 | 2030 October 28 16:00 |  |  | 3
655 | Yes | Auto Scheduled | Project Inputs | 886 days | 2025 December 15 08:00 | 2029 May 07 16:00 |  |  | 4
656 | Yes | Auto Scheduled | Work performed prior to TPP | 20 days | 2025 December 15 08:00 | 2026 January 09 16:00 | 584SS-20d |  | 5
657 | Yes | Auto Scheduled | PFS - for characterisation | 0 days | 2026 April 10 16:00 | 2026 April 10 16:00 | 656FS+65d |  | 5
658 | Yes | Auto Scheduled | Dose decision Funds & FTEs | 0 days | 2026 July 10 16:00 | 2026 July 10 16:00 | 656FS+130d |  | 5
659 | Yes | Auto Scheduled | PFS - non GMP | 0 days | 2027 January 25 16:00 | 2027 January 25 16:00 | 778 |  | 5
660 | Yes | Auto Scheduled | PFS - GMP | 0 days | 2027 May 31 16:00 | 2027 May 31 16:00 | 782 |  | 5
661 | Yes | Auto Scheduled | PFS - PV | 0 days | 2029 May 07 16:00 | 2029 May 07 16:00 | 914 |  | 5
662 | Yes | Auto Scheduled | Clinical Image Development | 890 days | 2025 December 15 08:00 | 2029 May 11 16:00 | 656SS |  | 4
663 | Yes | Auto Scheduled | Initial Concept Phase | 130 days | 2025 December 15 08:00 | 2026 June 12 16:00 | 656SS |  | 5
664 | Yes | Auto Scheduled | Prep for Design Assessment | 85 days | 2026 July 13 08:00 | 2026 November 06 16:00 | 658 |  | 5
665 | Yes | Auto Scheduled | Design Assessment | 35 days | 2026 November 09 08:00 | 2026 December 25 16:00 | 664 |  | 5
666 | Yes | Auto Scheduled | Prep for Design Verification | 55 days | 2026 December 28 08:00 | 2027 March 12 16:00 | 665 |  | 5
667 | Yes | Auto Scheduled | Design Verification and Sub-Assy PV | 85 days | 2027 March 15 08:00 | 2027 July 09 16:00 | 666 |  | 5
668 | Yes | Auto Scheduled | Human Factors Pre-clinical | 65 days | 2027 June 14 08:00 | 2027 September 10 16:00 | 667FS-20d |  | 5
669 | Yes | Auto Scheduled | PFP Assembly | 65 days | 2027 July 12 08:00 | 2027 October 08 16:00 | 592SS-155d,667 |  | 5
670 | Yes | Auto Scheduled | PFP Pack and Label | 65 days | 2027 October 11 08:00 | 2028 January 07 16:00 | 669 |  | 5
671 | Yes | Auto Scheduled | Devices available for clinical use | 0 days | 2028 January 07 16:00 | 2028 January 07 16:00 | 670 |  | 5
672 | Yes | Auto Scheduled | Shipping to clinical sites | 25 days | 2028 January 10 08:00 | 2028 February 11 16:00 | 671 |  | 5
673 | Yes | Auto Scheduled | Ph 3 Clinical study start (PFP start) | 0 days | 2028 February 11 16:00 | 2028 February 11 16:00 | 672 |  | 5
674 | Yes | Auto Scheduled | Planned returns (evaluation of post-use devices) | 65 days | 2029 February 12 08:00 | 2029 May 11 16:00 | 673FS+260d |  | 5
675 | Yes | Auto Scheduled | Commercial Image Development | 515 days | 2028 May 09 08:00 | 2030 April 29 16:00 |  |  | 4
676 | Yes | Auto Scheduled | Commercial image development | 260 days | 2028 May 09 08:00 | 2029 May 07 16:00 | 661FF |  | 5
677 | Yes | Auto Scheduled | Human Factors Summative | 85 days | 2029 July 03 08:00 | 2029 October 29 16:00 | 676,661FS+40d |  | 5
678 | Yes | Auto Scheduled | Process Characterisation | 65 days | 2029 July 03 08:00 | 2029 October 01 16:00 | 661FS+40d,676 |  | 5
679 | Yes | Auto Scheduled | Device Assembly PV | 85 days | 2029 October 02 08:00 | 2030 January 28 16:00 | 678 |  | 5
680 | Yes | Auto Scheduled | HFER (Human Factors Engineering Report) | 45 days | 2029 October 30 08:00 | 2029 December 31 16:00 | 677 |  | 5
681 | Yes | Auto Scheduled | Shipping study | 65 days | 2030 January 29 08:00 | 2030 April 29 16:00 | 679 |  | 5
682 | Yes | Auto Scheduled | Device information for BLA | 130 days | 2030 April 30 08:00 | 2030 October 28 16:00 |  |  | 4
683 | Yes | Auto Scheduled | Authoring device sections of BLA | 65 days | 2030 April 30 08:00 | 2030 July 29 16:00 | 681,680,674 |  | 5
684 | Yes | Auto Scheduled | Expected publishing time | 65 days | 2030 July 30 08:00 | 2030 October 28 16:00 | 683 |  | 5
685 | Yes | Auto Scheduled | Expected BLA submission-ready based on device sections | 0 days | 2030 October 28 16:00 | 2030 October 28 16:00 | 684 |  | 5
686 | Yes | Auto Scheduled | Stability (device) | 695 days | 2027 May 31 16:00 | 2030 January 28 16:00 |  |  | 4
687 | Yes | Auto Scheduled | Development stability - Time 0 | 0 days | 2027 May 31 16:00 | 2027 May 31 16:00 | 660 |  | 5
688 | Yes | Auto Scheduled | Clinical stability - Time 0 | 0 days | 2027 October 08 16:00 | 2027 October 08 16:00 | 669 |  | 5
689 | Yes | Auto Scheduled | Commercial stability - Time 0 | 0 days | 2030 January 28 16:00 | 2030 January 28 16:00 | 679 |  | 5
690 | Yes | Auto Scheduled | Commercial Analytical Development | 1236 days | 2025 September 29 08:00 | 2030 June 24 16:00 |  |  | 3
691 | Yes | Auto Scheduled | ARD Gap analysis (Qualification/Spec Eval) | 120 days | 2025 September 29 08:00 | 2026 March 13 16:00 |  |  | 4
692 | Yes | Auto Scheduled | Quality Attributes Assessment (identify; rate; and collate) | 5 days | 2026 January 12 08:00 | 2026 January 16 16:00 | 583 |  | 5
693 | Yes | Auto Scheduled | Method assessment | 120 days | 2025 September 29 08:00 | 2026 March 13 16:00 |  |  | 5
694 | Yes | Auto Scheduled | Evaluation of formulation change impact (Lyo to Liquid) | 10 days | 2026 January 19 08:00 | 2026 January 30 16:00 | 692 |  | 6
695 | Yes | Auto Scheduled | Evaluate Specifications | 5 days | 2026 January 19 08:00 | 2026 January 23 16:00 | 694SS |  | 6
696 | Yes | Auto Scheduled | Bioassay(s) assessment | 10 days | 2025 September 29 08:00 | 2025 October 10 16:00 | 694SS-80d |  | 6
697 | Yes | Auto Scheduled | Stability indicating assessment (forced degradation studies?) | 40 days | 2026 January 19 08:00 | 2026 March 13 16:00 | 694SS |  | 6
698 | Yes | Auto Scheduled | Assess method readiness for validation (with PGS) | 10 days | 2026 March 02 08:00 | 2026 March 13 16:00 | 696,697FF,694 |  | 6
699 | Yes | Auto Scheduled | Structure Function assessment with ICH DP material | 200 days | 2027 January 12 08:00 | 2027 October 18 16:00 | 777 |  | 4
700 | Yes | Auto Scheduled | Method development & qualification | 300 days | 2025 October 13 08:00 | 2026 December 04 16:00 |  |  | 4
701 | Yes | Auto Scheduled | Bioassay Methods | 300 days | 2025 October 13 08:00 | 2026 December 04 16:00 |  |  | 5
702 | Yes | Auto Scheduled | Bioassay development & qualification | 260 days | 2025 October 13 08:00 | 2026 October 09 16:00 | 696 |  | 6
703 | Yes | Auto Scheduled | Define bridging studies for new/changed methods (Bioassay) | 5 days | 2026 October 05 08:00 | 2026 October 09 16:00 | 702FF |  | 6
704 | Yes | Auto Scheduled | Execute bridging studies for new/changed methods (Bioassay) | 40 days | 2026 October 12 08:00 | 2026 December 04 16:00 | 703 |  | 6
705 | Yes | Auto Scheduled | Non-Bioassay Methods | 120 days | 2026 March 16 08:00 | 2026 August 28 16:00 |  |  | 5
706 | Yes | Auto Scheduled | New/revised Methods (1-2 methods) | 60 days | 2026 March 16 08:00 | 2026 June 05 16:00 | 693 |  | 6
707 | Yes | Auto Scheduled | Method Qualification | 20 days | 2026 June 08 08:00 | 2026 July 03 16:00 | 706 |  | 6
708 | Yes | Auto Scheduled | Define bridging studies for new/changed methods (Non-Bioassay) | 5 days | 2026 June 29 08:00 | 2026 July 03 16:00 | 707FF |  | 6
709 | Yes | Auto Scheduled | Execute bridging studies for new/changed methods (Non-Bioassay) | 40 days | 2026 July 06 08:00 | 2026 August 28 16:00 | 708 |  | 6
710 | Yes | Auto Scheduled | BRD Support | 401 days | 2026 January 12 08:00 | 2027 July 26 16:00 |  |  | 4
711 | Yes | Auto Scheduled | Phase3 Upstream process development | 110 days | 2026 January 12 08:00 | 2026 June 12 16:00 | 607SS |  | 5
712 | Yes | Auto Scheduled | Phase3 Downstream process development | 110 days | 2026 February 09 08:00 | 2026 July 10 16:00 | 608SS |  | 5
713 | Yes | Auto Scheduled | TS4/Engineering Batch Inprocess Sample Testing for information only | 15 days | 2026 September 15 08:00 | 2026 October 05 16:00 | 612 |  | 5
714 | Yes | Auto Scheduled | TS4 Analytical Characterization | 20 days | 2026 September 15 08:00 | 2026 October 12 16:00 | 612 |  | 5
715 | Yes | Auto Scheduled | Method Transfer to CRO - Matrix verification for inprocess & release methods for | 30 days | 2027 June 15 08:00 | 2027 July 26 16:00 | 864SS+20d |  | 5
716 | Yes | Auto Scheduled | E&L Studies | 1055 days | 2026 June 09 08:00 | 2030 June 24 16:00 |  |  | 4
717 | Yes | Auto Scheduled | Extractables and Leachables Method Development | 0 days | 2026 August 04 08:00 | 2026 August 04 08:00 | 719SF |  | 5
718 | Yes | Auto Scheduled | DS & DP Contact Risk Assment/Identify Leachables | 40 days | 2026 June 09 08:00 | 2026 August 04 08:00 | 719SF |  | 5
719 | Yes | Auto Scheduled | Develop & validate leachables target methods | 120 days | 2026 August 04 08:00 | 2027 January 19 08:00 | 721SF |  | 5
720 | Yes | Auto Scheduled | DS E&L Stability | 850 days | 2027 January 19 08:00 | 2030 April 22 16:00 |  |  | 5
721 | Yes | Auto Scheduled | Stability Initiation; Admin Support | 30 days | 2027 January 19 08:00 | 2027 March 02 08:00 | 722SF |  | 6
722 | Yes | Auto Scheduled | E&L DS Stability Study - T0 | 20 days | 2027 March 02 08:00 | 2027 March 29 16:00 | 752FS+10d |  | 6
723 | Yes | Auto Scheduled | DS Stability Study - 6 month pull point | 20 days | 2027 September 28 08:00 | 2027 October 25 16:00 | 722FS+130d |  | 6
724 | Yes | Auto Scheduled | DS Stability Study - 12 month pull point | 20 days | 2028 March 28 08:00 | 2028 April 24 16:00 | 722FS+260d |  | 6
725 | Yes | Auto Scheduled | DS Stability Study - 24 month pull point | 20 days | 2029 March 27 08:00 | 2029 April 23 16:00 | 722FS+520d |  | 6
726 | Yes | Auto Scheduled | DS Stability Study - 36 month pull point | 20 days | 2030 March 26 08:00 | 2030 April 22 16:00 | 722FS+780d |  | 6
727 | Yes | Auto Scheduled | DP E&L Stability | 850 days | 2027 March 23 08:00 | 2030 June 24 16:00 |  |  | 5
728 | Yes | Auto Scheduled | Stability Initiation; Admin Support | 30 days | 2027 March 23 08:00 | 2027 May 04 08:00 | 729SF |  | 6
729 | Yes | Auto Scheduled | E&L DP Stability Study - T0 | 20 days | 2027 May 04 08:00 | 2027 May 31 16:00 | 781FS+10d |  | 6
730 | Yes | Auto Scheduled | DP Stability Study - 6 month pull point | 20 days | 2027 November 30 08:00 | 2027 December 27 16:00 | 729FS+130d |  | 6
731 | Yes | Auto Scheduled | DP Stability Study - 12 month pull point | 20 days | 2028 May 30 08:00 | 2028 June 26 16:00 | 729FS+260d |  | 6
732 | Yes | Auto Scheduled | DP Stability Study - 24 month pull point | 20 days | 2029 May 29 08:00 | 2029 June 25 16:00 | 729FS+520d |  | 6
733 | Yes | Auto Scheduled | DP Stability Study - 36 month pull point | 20 days | 2030 May 28 08:00 | 2030 June 24 16:00 | 729FS+780d |  | 6
734 | Yes | Auto Scheduled | Method Co-Validation (Method Co-Validation (with PGRD driving timeline and PGS s | 355 days | 2026 December 07 08:00 | 2028 April 14 16:00 |  |  | 4
735 | Yes | Auto Scheduled | DS & DP Method validation (IPC & Release) | 355 days | 2026 December 07 08:00 | 2028 April 14 16:00 |  |  | 5
736 | Yes | Auto Scheduled | Protocol authoring and approval | 40 days | 2026 December 07 08:00 | 2027 January 29 16:00 | 700 |  | 6
737 | Yes | Auto Scheduled | Tech transfer and sample prep | 190 days | 2027 February 01 08:00 | 2027 October 22 16:00 | 736 |  | 6
738 | Yes | Auto Scheduled | Method Validation Protocol Execution | 60 days | 2027 October 25 08:00 | 2028 January 14 16:00 | 737 |  | 6
739 | Yes | Auto Scheduled | Method Validation Protocol Execution - Cell based assay | 125 days | 2027 October 25 08:00 | 2028 April 14 16:00 | 738SS |  | 6
740 | Yes | Auto Scheduled | Report writing | 40 days | 2028 January 17 08:00 | 2028 March 10 16:00 | 738 |  | 6
741 | Yes | Auto Scheduled | Method Validation Complete | 0 days | 2028 March 10 16:00 | 2028 March 10 16:00 | 740 |  | 6
742 | Yes | Auto Scheduled | Identify/Develop Comparators | 508 days | 2025 May 29 08:00 | 2027 May 10 16:00 |  |  | 2
743 | Yes | Auto Scheduled | Comparator Development | 260 days | 2025 May 29 08:00 | 2026 May 27 16:00 | 592FF-378d |  | 3
744 | Yes | Auto Scheduled | Comparators for P3 | 260 days | 2026 May 12 08:00 | 2027 May 10 16:00 | 592FF-130d |  | 3
745 | Yes | Auto Scheduled | Manufacture for CoDev to Phase 3; ICH & Launch | 755 days | 2026 October 06 08:00 | 2029 August 27 16:00 |  |  | 2
746 | Yes | Auto Scheduled | Manufacture P3/ICH Material | 755 days | 2026 October 06 08:00 | 2029 August 27 16:00 |  |  | 3
747 | Yes | Auto Scheduled | Manufacture P3/ICH Drug Substance | 160 days | 2026 October 13 08:00 | 2027 May 24 16:00 |  |  | 4
748 | Yes | Auto Scheduled | Tech Transfer for P3/ICH Drug Substance | 40 days | 2026 October 13 08:00 | 2026 December 07 16:00 | 611 |  | 5
749 | Yes | Auto Scheduled | Method Transfer- Inprocess Methods (new Site/CRO) | 30 days | 2026 October 27 08:00 | 2026 December 07 16:00 | 748FF |  | 5
750 | Yes | Auto Scheduled | Phase3/ICH DS & DP Specifications development & approval | 30 days | 2026 October 27 08:00 | 2026 December 08 08:00 | 752SF |  | 5
751 | Yes | Auto Scheduled | Raws/Resins & Plasmids for P3/ICH GMP Mfg | 1 day | 2026 November 10 08:00 | 2026 November 10 16:00 | 752SS-20d |  | 5
752 | Yes | Auto Scheduled | Manufacture Phase 3/ICH Drug Substance | 50 days | 2026 December 08 08:00 | 2027 February 15 16:00 | 748,602 |  | 5
753 | Yes | Auto Scheduled | DS IPC Testing | 30 days | 2027 January 05 08:00 | 2027 February 15 16:00 | 752FF |  | 5
754 | Yes | Auto Scheduled | Bulk Harvest testing (Batch 1) | 50 days | 2027 January 12 08:00 | 2027 March 22 16:00 | 752FS-25d |  | 5
755 | Yes | Auto Scheduled | P3 / ICH DS Release Testing (Batch 1) | 20 days | 2027 January 19 08:00 | 2027 February 15 16:00 | 752SS+30d |  | 5
756 | Yes | Auto Scheduled | micro method qualification endo; bio sterility | 20 days | 2027 January 19 08:00 | 2027 February 15 16:00 | 755SS |  | 5
757 | Yes | Auto Scheduled | use period- DS | 5 days | 2027 February 16 08:00 | 2027 February 22 16:00 | 755 |  | 5
758 | Yes | Auto Scheduled | Bulk Harvest testing (Batch 2-3) | 50 days | 2027 February 09 08:00 | 2027 April 19 16:00 | 752FS-5d |  | 5
759 | Yes | Auto Scheduled | P3 / ICH DS Release Testing (Batch 2-3) | 20 days | 2027 February 16 08:00 | 2027 March 15 16:00 | 752 |  | 5
760 | Yes | Auto Scheduled | Interim Release P3/ICH Drug Substance (batch 1) | 10 days | 2027 February 16 08:00 | 2027 March 01 16:00 | 755 |  | 5
761 | Yes | Auto Scheduled | GMP DS Mfg Inprocess Sample testing for Information only | 25 days | 2027 February 16 08:00 | 2027 March 22 16:00 | 752 |  | 5
762 | Yes | Auto Scheduled | Ship P3/ICH Drug Substance to DP mfg site | 10 days | 2027 March 02 08:00 | 2027 March 15 16:00 | 760 |  | 5
763 | Yes | Auto Scheduled | Virus removal / inactivation studies (CoDev) | 50 days | 2027 March 16 08:00 | 2027 May 24 16:00 | 752FS+20d |  | 5
764 | Yes | Auto Scheduled | Final Disposition P3/ICH Drug Substance (batch 1) | 10 days | 2027 May 11 08:00 | 2027 May 24 16:00 | 763FF,754,755 |  | 5
765 | Yes | Auto Scheduled | Phase 3/ICH GMP DS Comparability & Reference Material Characterization | 80 days | 2027 February 02 08:00 | 2027 May 24 16:00 |  |  | 5
766 | Yes | Auto Scheduled | Primary ref material dilution & prep protocol written | 0 days | 2027 February 02 08:00 | 2027 February 02 08:00 | 767FS-20d |  | 6
767 | Yes | Auto Scheduled | Vial primary reference material | 10 days | 2027 February 16 08:00 | 2027 March 01 16:00 | 752 |  | 6
768 | Yes | Auto Scheduled | P3/ICH DS Vialing/label/Storage/Uniformity Testing | 10 days | 2027 February 16 08:00 | 2027 March 01 16:00 | 752 |  | 6
769 | Yes | Auto Scheduled | P3/ICH DS Characterization & Comparability- Primary Structure | 60 days | 2027 March 02 08:00 | 2027 May 24 16:00 | 768 |  | 6
770 | Yes | Auto Scheduled | P3/ICH DS Characterization & Comparability- Post-translational Modifications | 60 days | 2027 March 02 08:00 | 2027 May 24 16:00 | 768 |  | 6
771 | Yes | Auto Scheduled | P3/ICH DS Characterization & Comparability- Prod Isoforms/Degradation Prod | 60 days | 2027 March 02 08:00 | 2027 May 24 16:00 | 768 |  | 6
772 | Yes | Auto Scheduled | P3/ICH DS Characterization & Comparability- Higher Order Structure | 60 days | 2027 March 02 08:00 | 2027 May 24 16:00 | 768 |  | 6
773 | Yes | Auto Scheduled | P3/ICH DS Characterization & Comparability- Biological Activity | 60 days | 2027 March 02 08:00 | 2027 May 24 16:00 | 768 |  | 6
774 | Yes | Auto Scheduled | Manufacture P3/ICH Drug Product | 185 days | 2026 October 06 08:00 | 2027 June 21 16:00 |  |  | 4
775 | Yes | Auto Scheduled | Tech transfer for P3/ICH Drug Product (PhRD to PGS) | 60 days | 2026 October 06 08:00 | 2026 December 29 08:00 | 637FF+10d,777SF |  | 5
776 | Yes | Auto Scheduled | Method Transfer- Inprocess Methods (new Site/CRO) | 30 days | 2026 November 17 08:00 | 2026 December 29 08:00 | 777SF |  | 5
777 | Yes | Auto Scheduled | Engineering Run | 10 days | 2026 December 29 08:00 | 2027 January 12 08:00 | 781SF-60d |  | 5
778 | Yes | Auto Scheduled | Product quality testing | 10 days | 2027 January 12 08:00 | 2027 January 25 16:00 | 777 |  | 5
779 | Yes | Auto Scheduled | micro method qualification endo; bio sterility | 20 days | 2026 December 29 08:00 | 2027 January 25 16:00 | 777SS |  | 5
780 | Yes | Auto Scheduled | DS receipt by DP site | 15 days | 2027 March 16 08:00 | 2027 April 05 16:00 | 762 |  | 5
781 | Yes | Auto Scheduled | P3/ICH DP mfg--Fill active (strength #1) - Lot 1 | 10 days | 2027 April 06 08:00 | 2027 April 19 16:00 | 780 |  | 5
782 | Yes | Auto Scheduled | DP Strength1 Release Testing | 30 days | 2027 April 20 08:00 | 2027 May 31 16:00 | 781 |  | 5
783 | Yes | Auto Scheduled | micro method qualification endo; bio sterility | 20 days | 2027 April 20 08:00 | 2027 May 17 16:00 | 782SS |  | 5
784 | Yes | Auto Scheduled | use period- DP | 5 days | 2027 June 01 08:00 | 2027 June 07 16:00 | 782 |  | 5
785 | Yes | Auto Scheduled | P3/ICH DP mfg--Fill active (strength #2) - Lot 1 | 10 days | 2027 April 20 08:00 | 2027 May 03 16:00 | 781 |  | 5
786 | Yes | Auto Scheduled | DP Strength2 Release Testing | 30 days | 2027 May 04 08:00 | 2027 June 14 16:00 | 785 |  | 5
787 | Yes | Auto Scheduled | micro method qualification endo; bio sterility | 20 days | 2027 May 04 08:00 | 2027 May 31 16:00 | 786SS |  | 5
788 | Yes | Auto Scheduled | use period- DP | 5 days | 2027 June 15 08:00 | 2027 June 21 16:00 | 786 |  | 5
789 | Yes | Auto Scheduled | P3/ICH DP mfg - Strength #1 - Lots 2 and 3 | 15 days | 2027 May 04 08:00 | 2027 May 24 16:00 | 785 |  | 5
790 | Yes | Auto Scheduled | P3/ICH DP mfg - Strength #2 - Lots 2 and 3 | 15 days | 2027 May 25 08:00 | 2027 June 14 16:00 | 789 |  | 5
791 | Yes | Auto Scheduled | Disposition P3/ICH GMP Drug Product (Strength #1) | 10 days | 2027 June 01 08:00 | 2027 June 14 16:00 | 782 |  | 5
792 | Yes | Auto Scheduled | Ship to pack label for P3/ICH | 10 days | 2027 June 01 08:00 | 2027 June 14 16:00 | 791FF |  | 5
793 | Yes | Auto Scheduled | SC Planning; Pack & Label for P3 | 660 days | 2027 February 16 08:00 | 2029 August 27 16:00 |  |  | 4
794 | Yes | Auto Scheduled | Clinical confirms country(ies) and study design | 0 days | 2027 June 01 08:00 | 2027 June 01 08:00 | 792SS |  | 5
795 | Yes | Auto Scheduled | CSA/CPR Approval P3/ICH | 10 days | 2027 June 01 08:00 | 2027 June 14 16:00 | 794 |  | 5
796 | Yes | Auto Scheduled | IRT development | 100 days | 2027 June 01 08:00 | 2027 October 18 16:00 | 794 |  | 5
797 | Yes | Auto Scheduled | Package & Label P3/ICH DP | 90 days | 2027 June 15 08:00 | 2027 October 18 16:00 | 795,792 |  | 5
798 | Yes | Auto Scheduled | QA release (RoA)/QP release P3/ICH Packaged CTM | 10 days | 2027 October 19 08:00 | 2027 November 01 16:00 | 797,791FF+1d |  | 5
799 | Yes | Auto Scheduled | Site Activation | 10 days | 2027 October 19 08:00 | 2027 November 02 08:00 | 801SF |  | 5
800 | Yes | Auto Scheduled | IRT activation | 10 days | 2027 November 02 08:00 | 2027 November 15 16:00 | 798 |  | 5
801 | Yes | Auto Scheduled | Ship P3 DP to Clinical site | 10 days | 2027 November 02 08:00 | 2027 November 15 16:00 | 797,798,589 |  | 5
802 | Yes | Auto Scheduled | Clinical Supplies at the Site(s) | 0 days | 2027 November 15 16:00 | 2027 November 15 16:00 | 801,590 |  | 5
803 | Yes | Auto Scheduled | Distribution and Storage Charges | 660 days | 2027 February 16 08:00 | 2029 August 27 16:00 | 752 |  | 5
804 | Yes | Auto Scheduled | Expense for Ph3 start Milestone payment to Lonza (Ph3 start) | 1 day | 2027 November 09 08:00 | 2027 November 09 16:00 | 592SS |  | 5
805 | Yes | Auto Scheduled | Stability Testing for CoDev to Phase 3 & ICH Materials | 1166 days | 2026 December 22 08:00 | 2031 June 10 16:00 |  |  | 2
806 | Yes | Auto Scheduled | Stability Testing for P3/ICH | 1166 days | 2026 December 22 08:00 | 2031 June 10 16:00 |  |  | 3
807 | Yes | Auto Scheduled | GMP P3/ICH Drug Substance Stability (48 mo) | 1101 days | 2026 December 22 08:00 | 2031 March 11 16:00 |  |  | 4
808 | Yes | Auto Scheduled | method transfer complete and approved. | 50 days | 2026 December 22 08:00 | 2027 March 02 08:00 | 810SF-10d |  | 5
809 | Yes | Auto Scheduled | Stability Initiation; Admin Support | 30 days | 2027 February 02 08:00 | 2027 March 16 08:00 | 810SF |  | 5
810 | Yes | Auto Scheduled | Phase 3/ICH DS Stability Study - Start Point | 1 day | 2027 March 16 08:00 | 2027 March 16 16:00 | 752FS+20d |  | 5
811 | Yes | Auto Scheduled | Phase 3/ICH DS Stability Study - 1 month pull point | 1 day | 2027 April 15 08:00 | 2027 April 15 16:00 | 810SS+22d |  | 5
812 | Yes | Auto Scheduled | Phase 3/ICH DS Stability Study - 3 month pull point | 1 day | 2027 June 15 08:00 | 2027 June 15 16:00 | 810SS+65d |  | 5
813 | Yes | Auto Scheduled | Phase 3/ICH DS Stability Study - 6 month pull point | 1 day | 2027 September 14 08:00 | 2027 September 14 16:00 | 810SS+130d |  | 5
814 | Yes | Auto Scheduled | Phase 3/ICH DS Stability Study - 9 month pull point | 1 day | 2027 December 14 08:00 | 2027 December 14 16:00 | 810SS+195d |  | 5
815 | Yes | Auto Scheduled | Phase 3/ICH DS Stability Study - 12 month pull point | 1 day | 2028 March 14 08:00 | 2028 March 14 16:00 | 810SS+260d |  | 5
816 | Yes | Auto Scheduled | Phase 3/ICH DS Stability Study - 18 month pull point | 1 day | 2028 September 12 08:00 | 2028 September 12 16:00 | 810SS+390d |  | 5
817 | Yes | Auto Scheduled | Phase 3/ICH DS Stability Study - 24 month pull point | 1 day | 2029 March 13 08:00 | 2029 March 13 16:00 | 810SS+520d |  | 5
818 | Yes | Auto Scheduled | Phase 3/ICH DS Stability Study - 30 month pull point | 1 day | 2029 September 11 08:00 | 2029 September 11 16:00 | 810SS+650d |  | 5
819 | Yes | Auto Scheduled | Phase 3/ICH DS Stability Study - 36 month pull point | 1 day | 2030 March 12 08:00 | 2030 March 12 16:00 | 810SS+780d |  | 5
820 | Yes | Auto Scheduled | Phase 3/ICH DS Stability Study - 42 month pull point | 1 day | 2030 September 10 08:00 | 2030 September 10 16:00 | 810SS+910d |  | 5
821 | Yes | Auto Scheduled | Phase 3/ICH DS Stability Study - 48 month pull point | 1 day | 2031 March 11 08:00 | 2031 March 11 16:00 | 810SS+1040d |  | 5
822 | Yes | Auto Scheduled | GMP P3/ICH Drug Product Stability (48 mo) 3 lots; strength 1 | 1101 days | 2027 March 02 08:00 | 2031 May 20 16:00 |  |  | 4
823 | Yes | Auto Scheduled | method transfer - define complete and approved - Assays to transfer prior to PV | 50 days | 2027 March 02 08:00 | 2027 May 11 08:00 | 825SF-10d |  | 5
824 | Yes | Auto Scheduled | Stability Initiation; Admin Support | 30 days | 2027 April 13 08:00 | 2027 May 25 08:00 | 825SF |  | 5
825 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - Start Point | 1 day | 2027 May 25 08:00 | 2027 May 25 16:00 | 789 |  | 5
826 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 1 month pull point | 1 day | 2027 June 24 08:00 | 2027 June 24 16:00 | 825SS+22d |  | 5
827 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 3 month pull point | 1 day | 2027 August 24 08:00 | 2027 August 24 16:00 | 825SS+65d |  | 5
828 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 6 month pull point | 1 day | 2027 November 23 08:00 | 2027 November 23 16:00 | 825SS+130d |  | 5
829 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 9 month pull point | 1 day | 2028 February 22 08:00 | 2028 February 22 16:00 | 825SS+195d |  | 5
830 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 12 month pull point | 1 day | 2028 May 23 08:00 | 2028 May 23 16:00 | 825SS+260d |  | 5
831 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 18 month pull point | 1 day | 2028 November 21 08:00 | 2028 November 21 16:00 | 825SS+390d |  | 5
832 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 24 month pull point | 1 day | 2029 May 22 08:00 | 2029 May 22 16:00 | 825SS+520d |  | 5
833 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 30 month pull point | 1 day | 2029 November 20 08:00 | 2029 November 20 16:00 | 825SS+650d |  | 5
834 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 36 month pull point | 1 day | 2030 May 21 08:00 | 2030 May 21 16:00 | 825SS+780d |  | 5
835 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 42 month pull point | 1 day | 2030 November 19 08:00 | 2030 November 19 16:00 | 825SS+910d |  | 5
836 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 48 month pull point | 1 day | 2031 May 20 08:00 | 2031 May 20 16:00 | 825SS+1040d |  | 5
837 | Yes | Auto Scheduled | GMP P3/ICH Drug Product Stability (48 mo) 3 lots; strength 2 | 1071 days | 2027 May 04 08:00 | 2031 June 10 16:00 |  |  | 4
838 | Yes | Auto Scheduled | Stability Initiation; Admin Support | 30 days | 2027 May 04 08:00 | 2027 June 15 08:00 | 839SF |  | 5
839 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - Start Point | 1 day | 2027 June 15 08:00 | 2027 June 15 16:00 | 790 |  | 5
840 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 1 month pull point | 1 day | 2027 July 15 08:00 | 2027 July 15 16:00 | 839SS+22d |  | 5
841 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 3 month pull point | 1 day | 2027 September 14 08:00 | 2027 September 14 16:00 | 839SS+65d |  | 5
842 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 6 month pull point | 1 day | 2027 December 14 08:00 | 2027 December 14 16:00 | 839SS+130d |  | 5
843 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 9 month pull point | 1 day | 2028 March 14 08:00 | 2028 March 14 16:00 | 839SS+195d |  | 5
844 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 12 month pull point | 1 day | 2028 June 13 08:00 | 2028 June 13 16:00 | 839SS+260d |  | 5
845 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 18 month pull point | 1 day | 2028 December 12 08:00 | 2028 December 12 16:00 | 839SS+390d |  | 5
846 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 24 month pull point | 1 day | 2029 June 12 08:00 | 2029 June 12 16:00 | 839SS+520d |  | 5
847 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 30 month pull point | 1 day | 2029 December 11 08:00 | 2029 December 11 16:00 | 839SS+650d |  | 5
848 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 36 month pull point | 1 day | 2030 June 11 08:00 | 2030 June 11 16:00 | 839SS+780d |  | 5
849 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 42 month pull point | 1 day | 2030 December 10 08:00 | 2030 December 10 16:00 | 839SS+910d |  | 5
850 | Yes | Auto Scheduled | Phase 3/ICH DP Stability Study - 48 month pull point | 1 day | 2031 June 10 08:00 | 2031 June 10 16:00 | 839SS+1040d |  | 5
851 | Yes | Auto Scheduled | Regulatory Documentation for P3 | 451 days | 2026 January 12 08:00 | 2027 October 04 16:00 |  |  | 2
852 | Yes | Auto Scheduled | On-going CMC documentation and strategy for P3 | 451 days | 2026 January 12 08:00 | 2027 October 04 16:00 |  |  | 3
853 | Yes | Auto Scheduled | BTx Trigger Start | 0 days | 2026 January 12 08:00 | 2026 January 12 08:00 | 583SS |  | 4
854 | Yes | Auto Scheduled | BTx Trigger End | 0 days | 2027 October 04 16:00 | 2027 October 04 16:00 | 588FF |  | 4
855 | Yes | Auto Scheduled | Health Authority Mtg Prep for P3 (eg. Scientific Advice (SA); Board of Healt | 130 days | 2026 August 18 08:00 | 2027 February 15 16:00 | 748SS-40d |  | 3
856 | Yes | Auto Scheduled | Author & review CMC sections for P3 IND/IMPD Amendment | 60 days | 2027 June 15 08:00 | 2027 September 06 16:00 | 782FS+10d,855,652FF,853FF |  | 3
857 | Yes | Auto Scheduled | LPQ | 784 days | 2027 March 23 08:00 | 2030 March 22 16:00 |  |  | 1
858 | Yes | Auto Scheduled | Team Activities - Phase 3 | 619 days | 2027 November 08 16:00 | 2030 March 22 16:00 | 592 |  | 2
859 | Yes | Auto Scheduled | PS BTx Start Trigger-P3 start | 0 days | 2027 November 08 16:00 | 2027 November 08 16:00 | 592 |  | 3
860 | Yes | Auto Scheduled | PS BTx End Trigger - P3 finish | 0 days | 2030 March 22 16:00 | 2030 March 22 16:00 | 593 |  | 3
861 | Yes | Auto Scheduled | DS Risk Assessment #1 Prep | 40 days | 2027 March 23 08:00 | 2027 May 17 16:00 | 752FS+25d |  | 2
862 | Yes | Auto Scheduled | DS Risk assessment #1 | 0 days | 2027 May 17 16:00 | 2027 May 17 16:00 | 861 |  | 2
863 | Yes | Auto Scheduled | LPQ Summary (DS) | 230 days | 2027 May 18 08:00 | 2028 April 03 16:00 |  |  | 2
864 | Yes | Auto Scheduled | USP LPQ Prep | 30 days | 2027 May 18 08:00 | 2027 June 28 16:00 | 862 |  | 3
865 | Yes | Auto Scheduled | DS LPQ Analytical Testing Support - impurities | 60 days | 2027 May 18 08:00 | 2027 August 09 16:00 | 864SS |  | 3
866 | Yes | Auto Scheduled | USP LPQ Execution | 130 days | 2027 June 29 08:00 | 2027 December 27 16:00 | 864 |  | 3
867 | Yes | Auto Scheduled | Matrix verification for inprocess & release methods for LPQ support | 30 days | 2027 June 15 08:00 | 2027 July 26 16:00 | 864SS+20d |  | 3
868 | Yes | Auto Scheduled | DS LPQ Analytical Testing Support | 210 days | 2027 June 15 08:00 | 2028 April 03 16:00 | 864SS+20d |  | 3
869 | Yes | Auto Scheduled | LPQ Genotypic Studies | 40 days | 2027 November 16 08:00 | 2028 January 10 16:00 | 866FS-30d |  | 3
870 | Yes | Auto Scheduled | USP LPQ Reports | 60 days | 2027 December 28 08:00 | 2028 March 20 16:00 | 866 |  | 3
871 | Yes | Auto Scheduled | DSP LPQ Prep | 10 days | 2027 May 18 08:00 | 2027 May 31 16:00 | 862 |  | 3
872 | Yes | Auto Scheduled | DSP LPQ Execution | 80 days | 2027 June 01 08:00 | 2027 September 20 16:00 | 871 |  | 3
873 | Yes | Auto Scheduled | DSP LPQ Reports | 60 days | 2027 September 21 08:00 | 2027 December 13 16:00 | 872 |  | 3
874 | Yes | Auto Scheduled | DS Risk Assessment #2 Prep | 40 days | 2027 December 28 08:00 | 2028 February 21 16:00 | 866,862,872 |  | 2
875 | Yes | Auto Scheduled | DS Risk assessment #2 | 0 days | 2028 February 21 16:00 | 2028 February 21 16:00 | 874 |  | 2
876 | Yes | Auto Scheduled | RFT/LPQ Planning & Performance DP Summary | 215 days | 2027 December 07 08:00 | 2028 October 02 16:00 |  |  | 2
877 | Yes | Auto Scheduled | DP LPQ studies | 215 days | 2027 December 07 08:00 | 2028 October 02 16:00 | 910SS-215d |  | 3
878 | Yes | Auto Scheduled | DP RFT/LPQ Analytical Testing Support | 140 days | 2028 February 15 08:00 | 2028 August 28 16:00 | 877SS+20d,879SS |  | 3
879 | Yes | Auto Scheduled | Execution of Experimental Plan (DP) | 0 days | 2028 February 14 16:00 | 2028 February 14 16:00 | 877SS+50d |  | 2
880 | Yes | Auto Scheduled | DP Risk assessment #2 | 0 days | 2028 October 02 16:00 | 2028 October 02 16:00 | 877FF |  | 2
881 | Yes | Auto Scheduled | Process Validation (PV) | 1621 days | 2027 February 16 08:00 | 2033 May 03 16:00 |  |  | 1
882 | Yes | Auto Scheduled | Manufacture Validation Material | 860 days | 2027 February 16 08:00 | 2030 June 03 16:00 |  |  | 2
883 | Yes | Auto Scheduled | DS Process Validation Activities | 640 days | 2027 February 16 08:00 | 2029 July 30 16:00 |  |  | 3
884 | Yes | Auto Scheduled | Process Validation Campaign (DS) Readiness | 265 days | 2027 February 16 08:00 | 2028 February 21 16:00 | 874FS-265d |  | 4
885 | Yes | Auto Scheduled | Spec Discussions | 10 days | 2027 December 28 08:00 | 2028 January 11 08:00 | 886SF |  | 4
886 | Yes | Auto Scheduled | PV DS & DP Targets/acceptance criteria development & approval | 30 days | 2028 January 11 08:00 | 2028 February 21 16:00 | 884FF |  | 4
887 | Yes | Auto Scheduled | Commercial DS & DP Specifications & approval | 120 days | 2028 February 15 08:00 | 2028 August 01 08:00 | 891SF |  | 4
888 | Yes | Auto Scheduled | TT for Process Validation (DS) | 115 days | 2028 February 22 08:00 | 2028 July 31 16:00 | 875 |  | 4
889 | Yes | Auto Scheduled | DS PV protocols written & approved | 1 day | 2028 July 04 08:00 | 2028 July 04 16:00 | 891SS-20d |  | 4
890 | Yes | Auto Scheduled | Raws/Resins & Plasmids for Validation GMP Mfg | 1 day | 2028 July 04 08:00 | 2028 July 04 16:00 | 891SS-20d |  | 4
891 | Yes | Auto Scheduled | Validation Manufacture DS (4 batches) | 60 days | 2028 August 01 08:00 | 2028 October 23 16:00 | 888 |  | 4
892 | Yes | Auto Scheduled | Support of PV runs DS (BRD) | 60 days | 2028 August 01 08:00 | 2028 October 23 16:00 | 891SS |  | 4
893 | Yes | Auto Scheduled | Bulk Harvest testing (CoDev) | 50 days | 2028 September 19 08:00 | 2028 November 27 16:00 | 891FS-25d |  | 4
894 | Yes | Auto Scheduled | PV DS Release Testing | 30 days | 2028 October 24 08:00 | 2028 December 04 16:00 | 891 |  | 4
895 | Yes | Auto Scheduled | Resin Cycling Studies | 200 days | 2028 October 24 08:00 | 2029 July 30 16:00 | 891 |  | 4
896 | Yes | Auto Scheduled | DS PV Reports Written & Approved | 180 days | 2028 October 24 08:00 | 2029 July 02 16:00 | 891 |  | 4
897 | Yes | Auto Scheduled | PV Campaign GMP DS Comparability | 40 days | 2028 October 24 08:00 | 2028 December 18 16:00 |  |  | 4
898 | Yes | Auto Scheduled | PV Comparability- Primary Structure | 40 days | 2028 October 24 08:00 | 2028 December 18 16:00 | 891 |  | 5
899 | Yes | Auto Scheduled | PV Comparability- Post-translational Modifications | 40 days | 2028 October 24 08:00 | 2028 December 18 16:00 | 891 |  | 5
900 | Yes | Auto Scheduled | PV Comparability- Product Isoforms/Degradation Products/Im | 40 days | 2028 October 24 08:00 | 2028 December 18 16:00 | 891 |  | 5
901 | Yes | Auto Scheduled | PV Comparability- Higher Order Structure | 40 days | 2028 October 24 08:00 | 2028 December 18 16:00 | 891 |  | 5
902 | Yes | Auto Scheduled | PV Comparability- Biological Activity | 40 days | 2028 October 24 08:00 | 2028 December 18 16:00 | 891 |  | 5
903 | Yes | Auto Scheduled | Validation DS QA Disposition | 10 days | 2028 December 05 08:00 | 2028 December 18 16:00 | 894 |  | 4
904 | Yes | Auto Scheduled | Ship Validation DS to DP Manufacture | 10 days | 2028 December 19 08:00 | 2029 January 01 16:00 | 903 |  | 4
905 | Yes | Auto Scheduled | LIVCA (Harvest of last DS batch plus 4 months for analysis) | 87 days | 2028 October 17 08:00 | 2029 February 14 16:00 | 891FS-5d |  | 4
906 | Yes | Auto Scheduled | Risk Assessment #3 Prep | 40 days | 2028 November 28 08:00 | 2029 January 22 16:00 | 891FS+25d |  | 3
907 | Yes | Auto Scheduled | DS Risk Assessment #3 | 0 days | 2029 January 22 16:00 | 2029 January 22 16:00 | 906 |  | 3
908 | Yes | Auto Scheduled | DP Process Validation Activities | 785 days | 2027 June 01 08:00 | 2030 June 03 16:00 |  |  | 3
909 | Yes | Auto Scheduled | Analytical Tech Transfer to 2nd PGS Site | 395 days | 2027 June 01 08:00 | 2028 December 05 08:00 | 912SF-20d |  | 4
910 | Yes | Auto Scheduled | Prep for Process Validation Campaign (DP) | 65 days | 2028 October 03 08:00 | 2029 January 01 16:00 | 912SS-65d |  | 4
911 | Yes | Auto Scheduled | DP PV protocols written & approved | 0 days | 2028 December 05 08:00 | 2028 December 05 08:00 | 912SS-20d |  | 4
912 | Yes | Auto Scheduled | Validation Manufacture DP (2 strengths) | 60 days | 2029 January 02 08:00 | 2029 March 26 16:00 | 904,649,650 |  | 4
913 | Yes | Auto Scheduled | Support of PV runs DP (PhRD) | 120 days | 2029 January 02 08:00 | 2029 June 18 16:00 | 912SS |  | 4
914 | Yes | Auto Scheduled | PV DP Release Testing | 30 days | 2029 March 27 08:00 | 2029 May 07 16:00 | 912 |  | 4
915 | Yes | Auto Scheduled | Data mining & stats analysis for specifications | 50 days | 2029 May 08 08:00 | 2029 July 16 16:00 | 914 |  | 4
916 | Yes | Auto Scheduled | DP PV Reports Written & Approved | 120 days | 2029 March 27 08:00 | 2029 September 10 16:00 | 912 |  | 4
917 | Yes | Auto Scheduled | PV disposition & Stability | 310 days | 2029 March 27 08:00 | 2030 June 03 16:00 | 912 |  | 4
918 | Yes | Auto Scheduled | DAI (Commercial Support) | 65 days | 2029 March 27 08:00 | 2029 June 25 16:00 | 912 |  | 4
919 | Yes | Auto Scheduled | Lot Genealogy Complete for PV Lots | 0 days | 2029 May 07 16:00 | 2029 May 07 16:00 | 912FS+30d |  | 4
920 | Yes | Auto Scheduled | Validation DP Disposition | 10 days | 2029 May 08 08:00 | 2029 May 21 16:00 | 914 |  | 4
921 | Yes | Auto Scheduled | Final CQAs after PV | 0 days | 2029 July 16 16:00 | 2029 July 16 16:00 | 912FS+80d |  | 4
922 | Yes | Auto Scheduled | Lot Genealogy Complete for PV Lots | 0 days | 2029 September 10 16:00 | 2029 September 10 16:00 | 916FF |  | 4
923 | Yes | Auto Scheduled | DP Risk Assessment #3 | 0 days | 2029 October 10 16:00 | 2029 October 10 16:00 | 918,916FS+22d |  | 3
924 | Yes | Auto Scheduled | Assemble Label Pack (ALP) activities | 146 days | 2029 June 20 08:00 | 2030 January 09 16:00 |  |  | 3
925 | Yes | Auto Scheduled | Assemble Label Pack (ALP) PQ protocol authoring and approval | 65 days | 2029 June 20 08:00 | 2029 September 19 08:00 | 926SF |  | 4
926 | Yes | Auto Scheduled | ALP PQ Execution | 15 days | 2029 September 19 08:00 | 2029 October 10 08:00 | 927SF |  | 4
927 | Yes | Auto Scheduled | ALP PQ analytical testing | 44 days | 2029 October 10 08:00 | 2029 December 11 08:00 | 928SF |  | 4
928 | Yes | Auto Scheduled | ALP PQ report authoring and approval | 22 days | 2029 December 11 08:00 | 2030 January 09 16:00 | 988FF-130d |  | 4
929 | Yes | Auto Scheduled | SC Planning; Pack & Label Validation Material | 120 days | 2029 May 08 08:00 | 2029 October 22 16:00 |  |  | 3
930 | Yes | Auto Scheduled | Ship to pack label | 10 days | 2029 May 08 08:00 | 2029 May 21 16:00 | 914 |  | 4
931 | Yes | Auto Scheduled | CSA/CPR Approval | 10 days | 2029 May 08 08:00 | 2029 May 21 16:00 | 930SS |  | 4
932 | Yes | Auto Scheduled | IRT development | 100 days | 2029 May 08 08:00 | 2029 September 24 16:00 | 931SS |  | 4
933 | Yes | Auto Scheduled | Package & Label validation material (for ongoing Clinical demand) | 90 days | 2029 May 22 08:00 | 2029 September 24 16:00 | 930,931 |  | 4
934 | Yes | Auto Scheduled | QA release (RoA)/QP release validation Material | 10 days | 2029 September 25 08:00 | 2029 October 08 16:00 | 933 |  | 4
935 | Yes | Auto Scheduled | Site Activation | 10 days | 2029 September 25 08:00 | 2029 October 09 08:00 | 937SF |  | 4
936 | Yes | Auto Scheduled | IRT Activation | 10 days | 2029 October 09 08:00 | 2029 October 22 16:00 | 934 |  | 4
937 | Yes | Auto Scheduled | Ship validation material | 10 days | 2029 October 09 08:00 | 2029 October 22 16:00 | 934,933 |  | 4
938 | Yes | Auto Scheduled | Stability Testing for Validation | 1221 days | 2028 August 29 08:00 | 2033 May 03 16:00 |  |  | 2
939 | Yes | Auto Scheduled | Validation Drug Substance Stability (48 mo) | 1101 days | 2028 August 29 08:00 | 2032 November 16 16:00 |  |  | 3
940 | Yes | Auto Scheduled | method transfer complete and approved | 50 days | 2028 August 29 08:00 | 2028 November 07 08:00 | 942SF-10d |  | 4
941 | Yes | Auto Scheduled | Stability Initiation; Admin Support | 30 days | 2028 October 10 08:00 | 2028 November 21 08:00 | 942SF |  | 4
942 | Yes | Auto Scheduled | Validation DS Stability Study - Start Point | 1 day | 2028 November 21 08:00 | 2028 November 21 16:00 | 891FS+20d |  | 4
943 | Yes | Auto Scheduled | Validation DS Stability Study - 1 month pull point | 1 day | 2028 December 21 08:00 | 2028 December 21 16:00 | 942SS+22d |  | 4
944 | Yes | Auto Scheduled | Validation DS Stability Study - 3 month pull point | 1 day | 2029 February 20 08:00 | 2029 February 20 16:00 | 942SS+65d |  | 4
945 | Yes | Auto Scheduled | Validation DS Stability Study - 6 month pull point | 1 day | 2029 May 22 08:00 | 2029 May 22 16:00 | 942SS+130d |  | 4
946 | Yes | Auto Scheduled | Validation DS Stability Study - 9 month pull point | 1 day | 2029 August 21 08:00 | 2029 August 21 16:00 | 942SS+195d |  | 4
947 | Yes | Auto Scheduled | Validation DS Stability Study - 12 month pull point | 1 day | 2029 November 20 08:00 | 2029 November 20 16:00 | 942SS+260d |  | 4
948 | Yes | Auto Scheduled | Validation DS Stability Study - 18 month pull point | 1 day | 2030 May 21 08:00 | 2030 May 21 16:00 | 942SS+390d |  | 4
949 | Yes | Auto Scheduled | Validation DS Stability Study - 24 month pull point | 1 day | 2030 November 19 08:00 | 2030 November 19 16:00 | 942SS+520d |  | 4
950 | Yes | Auto Scheduled | Validation DS Stability Study - 30 month pull point | 1 day | 2031 May 20 08:00 | 2031 May 20 16:00 | 942SS+650d |  | 4
951 | Yes | Auto Scheduled | Validation DS Stability Study - 36 month pull point | 1 day | 2031 November 18 08:00 | 2031 November 18 16:00 | 942SS+780d |  | 4
952 | Yes | Auto Scheduled | Validation DS Stability Study - 42 month pull point | 1 day | 2032 May 18 08:00 | 2032 May 18 16:00 | 942SS+910d |  | 4
953 | Yes | Auto Scheduled | Validation DS Stability Study - 48 month pull point | 1 day | 2032 November 16 08:00 | 2032 November 16 16:00 | 942SS+1040d |  | 4
954 | Yes | Auto Scheduled | Validation Drug Product Stability-Strength 1 (48 mo) | 1111 days | 2028 December 19 08:00 | 2033 March 22 16:00 |  |  | 3
955 | Yes | Auto Scheduled | method transfer complete and approved | 60 days | 2028 December 19 08:00 | 2029 March 13 08:00 | 957SF-10d |  | 4
956 | Yes | Auto Scheduled | Stability Initiation; Admin Support | 50 days | 2029 January 16 08:00 | 2029 March 27 08:00 | 957SF |  | 4
957 | Yes | Auto Scheduled | Validation DP Stability Study - Start Point | 1 day | 2029 March 27 08:00 | 2029 March 27 16:00 | 912 |  | 4
958 | Yes | Auto Scheduled | Validation DP Stability Study - 1 month pull point | 1 day | 2029 April 26 08:00 | 2029 April 26 16:00 | 957SS+22d |  | 4
959 | Yes | Auto Scheduled | Validation DP Stability Study - 3 month pull point | 1 day | 2029 June 26 08:00 | 2029 June 26 16:00 | 957SS+65d |  | 4
960 | Yes | Auto Scheduled | Validation DP Stability Study - 6 month pull point | 1 day | 2029 September 25 08:00 | 2029 September 25 16:00 | 957SS+130d |  | 4
961 | Yes | Auto Scheduled | Validation DP Stability Study - 9 month pull point | 1 day | 2029 December 25 08:00 | 2029 December 25 16:00 | 957SS+195d |  | 4
962 | Yes | Auto Scheduled | Validation DP Stability Study - 12 month pull point | 1 day | 2030 March 26 08:00 | 2030 March 26 16:00 | 957SS+260d |  | 4
963 | Yes | Auto Scheduled | Validation DP Stability Study - 18 month pull point | 1 day | 2030 September 24 08:00 | 2030 September 24 16:00 | 957SS+390d |  | 4
964 | Yes | Auto Scheduled | Validation DP Stability Study - 24 month pull point | 1 day | 2031 March 25 08:00 | 2031 March 25 16:00 | 957SS+520d |  | 4
965 | Yes | Auto Scheduled | Validation DP Stability Study - 30 month pull point | 1 day | 2031 September 23 08:00 | 2031 September 23 16:00 | 957SS+650d |  | 4
966 | Yes | Auto Scheduled | Validation DP Stability Study - 36 month pull point | 1 day | 2032 March 23 08:00 | 2032 March 23 16:00 | 957SS+780d |  | 4
967 | Yes | Auto Scheduled | Validation DP Stability Study - 42 month pull point | 1 day | 2032 September 21 08:00 | 2032 September 21 16:00 | 957SS+910d |  | 4
968 | Yes | Auto Scheduled | Validation DP Stability Study - 48 month pull point | 1 day | 2033 March 22 08:00 | 2033 March 22 16:00 | 957SS+1040d |  | 4
969 | Yes | Auto Scheduled | Validation Drug Product Stability-Strength 2 (48 mo) | 1071 days | 2029 March 27 08:00 | 2033 May 03 16:00 |  |  | 3
970 | Yes | Auto Scheduled | Stability Initiation; Admin Support | 30 days | 2029 March 27 08:00 | 2029 May 08 08:00 | 971SF |  | 4
971 | Yes | Auto Scheduled | Validation DP Stability Study - Start Point | 1 day | 2029 May 08 08:00 | 2029 May 08 16:00 | 912FS+30d |  | 4
972 | Yes | Auto Scheduled | Validation DP Stability Study - 1 month pull point | 1 day | 2029 June 07 08:00 | 2029 June 07 16:00 | 971SS+22d |  | 4
973 | Yes | Auto Scheduled | Validation DP Stability Study - 3 month pull point | 1 day | 2029 August 07 08:00 | 2029 August 07 16:00 | 971SS+65d |  | 4
974 | Yes | Auto Scheduled | Validation DP Stability Study - 6 month pull point | 1 day | 2029 November 06 08:00 | 2029 November 06 16:00 | 971SS+130d |  | 4
975 | Yes | Auto Scheduled | Validation DP Stability Study - 9 month pull point | 1 day | 2030 February 05 08:00 | 2030 February 05 16:00 | 971SS+195d |  | 4
976 | Yes | Auto Scheduled | Validation DP Stability Study - 12 month pull point | 1 day | 2030 May 07 08:00 | 2030 May 07 16:00 | 971SS+260d |  | 4
977 | Yes | Auto Scheduled | Validation DP Stability Study - 18 month pull point | 1 day | 2030 November 05 08:00 | 2030 November 05 16:00 | 971SS+390d |  | 4
978 | Yes | Auto Scheduled | Validation DP Stability Study - 24 month pull point | 1 day | 2031 May 06 08:00 | 2031 May 06 16:00 | 971SS+520d |  | 4
979 | Yes | Auto Scheduled | Validation DP Stability Study - 30 month pull point | 1 day | 2031 November 04 08:00 | 2031 November 04 16:00 | 971SS+650d |  | 4
980 | Yes | Auto Scheduled | Validation DP Stability Study - 36 month pull point | 1 day | 2032 May 04 08:00 | 2032 May 04 16:00 | 971SS+780d |  | 4
981 | Yes | Auto Scheduled | Validation DP Stability Study - 42 month pull point | 1 day | 2032 November 02 08:00 | 2032 November 02 16:00 | 971SS+910d |  | 4
982 | Yes | Auto Scheduled | Validation DP Stability Study - 48 month pull point | 1 day | 2033 May 03 08:00 | 2033 May 03 16:00 | 971SS+1040d |  | 4
983 | Yes | Auto Scheduled | Regulatory Documentation for BLA Submission | 1058 days | 2027 October 04 16:00 | 2031 October 23 16:00 |  |  | 2
984 | Yes | Auto Scheduled | On-going CMC documentation and strategy for BLA | 797 days | 2027 October 04 16:00 | 2030 October 23 16:00 |  |  | 3
985 | Yes | Auto Scheduled | BTx Trigger Start | 0 days | 2027 October 04 16:00 | 2027 October 04 16:00 | 852 |  | 4
986 | Yes | Auto Scheduled | BTx Trigger End | 0 days | 2030 October 23 16:00 | 2030 October 23 16:00 | 594FF |  | 4
987 | Yes | Auto Scheduled | BLA/MAA Kick Off Meeting | 0 days | 2028 August 09 16:00 | 2028 August 09 16:00 | 593FF-422d |  | 3
988 | Yes | Auto Scheduled | BLA/MAA Authorship | 500 days | 2028 August 10 08:00 | 2030 July 10 16:00 | 987 |  | 3
989 | Yes | Auto Scheduled | Health Authority Mtg Prep for BLA (eg. Scientific Advice (SA); Board of Heal | 130 days | 2029 July 12 08:00 | 2030 January 09 16:00 | 988FF-130d |  | 3
990 | Yes | Auto Scheduled | ICH DP Stability 18 mo data available | 0 days | 2029 March 13 16:00 | 2029 March 13 16:00 | 845FS+65d |  | 3
991 | Yes | Auto Scheduled | ICH DP Stability 24 mo data available | 0 days | 2029 September 11 16:00 | 2029 September 11 16:00 | 846FS+65d |  | 3
992 | Yes | Auto Scheduled | Validation DP 12 mo Stability data available | 0 days | 2030 June 04 16:00 | 2030 June 04 16:00 | 976FS+20d |  | 3
993 | Yes | Auto Scheduled | BLA BTx Complete | 0 days | 2030 August 27 16:00 | 2030 August 27 16:00 | 988FS+34d |  | 3
994 | Yes | Auto Scheduled | PAI Readiness | 65 days | 2030 June 25 08:00 | 2030 September 24 08:00 | 594SF-22d |  | 3
995 | Yes | Auto Scheduled | PAI (Prior Approval Inspection) | 10 days | 2031 January 23 08:00 | 2031 February 05 16:00 | 594FS+65d |  | 3
996 | Yes | Auto Scheduled | Design History File (DHF) Transfer to PGS | 1 day | 2031 August 07 08:00 | 2031 August 07 16:00 | 995FS+130d |  | 3
997 | Yes | Auto Scheduled | Expense for milestone payment to Lonza (BLA submission) | 1 day | 2030 October 24 08:00 | 2030 October 24 16:00 | 594 |  | 3
998 | Yes | Auto Scheduled | BLA Queries | 217 days | 2030 November 07 08:00 | 2031 September 05 16:00 | 594FS+10d |  | 3
999 | Yes | Auto Scheduled | Expense for milestone payment to Lonza (Approval of submission) | 1 day | 2031 October 23 08:00 | 2031 October 23 16:00 | 594FS+260d |  | 3
1000 | Yes | Auto Scheduled | EMA MAA Prep and Submission | 87 days | 2030 August 28 08:00 | 2030 December 26 16:00 | 993 |  | 3
1001 | Yes | Auto Scheduled | EMA MAA Queries | 175 days | 2030 December 27 08:00 | 2031 August 28 16:00 | 1000 |  | 3
1002 | Yes | Auto Scheduled | J-NDA Authorship | 130 days | 2030 September 05 08:00 | 2031 March 05 16:00 | 988FS+40d |  | 3
1003 | Yes | Auto Scheduled | [BTx date] J-NDA Submission | 0 days | 2031 March 05 16:00 | 2031 March 05 16:00 | 1002 |  | 3
1004 | Yes | Auto Scheduled | J-NDA Queries | 110 days | 2031 May 08 08:00 | 2031 October 08 16:00 | 1003FS+45d |  | 3
1005 | Yes | Auto Scheduled | Team Activities - Registration | 153 days | 2030 March 22 16:00 | 2030 October 23 16:00 | 858 |  | 2
1006 | Yes | Auto Scheduled | PS BTx Start Trigger | 0 days | 2030 March 22 16:00 | 2030 March 22 16:00 | 593 |  | 3
1007 | Yes | Auto Scheduled | PS BTx End Trigger | 0 days | 2030 October 23 16:00 | 2030 October 23 16:00 | 594 |  | 3
1008 | Yes | Auto Scheduled | Pre-Approval Inspection Support | 120 days | 2030 October 24 08:00 | 2031 April 09 16:00 |  |  | 1
1009 | Yes | Auto Scheduled | Assist commercial site with documentation to support commercial process | 120 days | 2030 October 24 08:00 | 2031 April 09 16:00 | 594 |  | 2
1010 | Yes | Auto Scheduled | Post-Filing Query Response & Final Label Approval | 120 days | 2030 October 24 08:00 | 2031 April 09 16:00 |  |  | 1
1011 | Yes | Auto Scheduled | Provide input to post filing questions | 120 days | 2030 October 24 08:00 | 2031 April 09 16:00 | 594 |  | 2
1012 | Yes | Auto Scheduled | Provide labwork to generate the data to respond to the queries | 120 days | 2030 October 24 08:00 | 2031 April 09 16:00 | 594 |  | 2
1013 | Yes | Auto Scheduled | Launch Support | 120 days | 2031 October 23 08:00 | 2032 April 07 16:00 |  |  | 1
1014 | Yes | Auto Scheduled | Meet with commercial to prepare for launch e.g. material supply & packaging etc | 120 days | 2031 October 23 08:00 | 2032 April 07 16:00 | 594SS+260d |  | 2
1015 | Yes | Auto Scheduled | Address agency questions | 120 days | 2031 October 23 08:00 | 2032 April 07 16:00 | 594SS+260d |  | 2
1016 | Yes | Auto Scheduled | Investigations as needed | 120 days | 2031 October 23 08:00 | 2032 April 07 16:00 | 594SS+260d |  | 2
1017 | Yes | Auto Scheduled | Releasing/testing commercial batches that are used for launch | 120 days | 2031 October 23 08:00 | 2032 April 07 16:00 | 594SS+260d |  | 2
1018 | Yes | Auto Scheduled | WRD Milestones | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 1
1019 | Yes | Auto Scheduled | Lead Development | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1020 | Yes | Auto Scheduled | Candidate Selection | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1021 | Yes | Auto Scheduled | Candidate Selection (CS) (CA plan date)#2 | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1022 | Yes | Auto Scheduled | Positive POM | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1023 | Yes | Auto Scheduled | J-NDA Approval | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1024 | Yes | Auto Scheduled | FIH Enabling Meeting | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1025 | Yes | Auto Scheduled | Compound Available to Start Reg Tox | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1026 | Yes | Auto Scheduled | FIH | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1027 | Yes | Auto Scheduled | FIP | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1028 | Yes | Auto Scheduled | Phase I Start | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1029 | Yes | Auto Scheduled | DSRD/Clinical Consensus Meeting | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1030 | Yes | Auto Scheduled | IND Filing | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1031 | Yes | Auto Scheduled | Phase IIa Start | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1032 | Yes | Auto Scheduled | POC | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1033 | Yes | Auto Scheduled | Decision to Invest in ICH/Registration Manufacture [TRIGGER: Pivotal Study Start | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1034 | Yes | Auto Scheduled | BTx_PS_Start_Peds | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1035 | Yes | Auto Scheduled | Phase III Start | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1036 | Yes | Auto Scheduled | MAA Submission | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1037 | Yes | Auto Scheduled | NDA Submission | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1038 | Yes | Auto Scheduled | NDA Approval | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1039 | Yes | Auto Scheduled | MAA Approval | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2
1040 | Yes | Auto Scheduled | SOCA | 0 days | 2021 January 01 00:00 | 2021 January 01 00:00 |  |  | 2